CPCCDE4002A Plan and supervise demolition work to minimise environmental and public health and safety impact

Release 1

CPCCDE4002A Plan and supervise demolition work to minimise environmental and public health and safety impact

Modification History

New unit.

This version first released with CPC08 Construction, Plumbing and Services Training Package Version 9.

Unit Descriptor

This unit of competency specifies the outcomes required to monitor and manage large demolition projects, including structures or installations above 15 metres, to minimise environmental and public health and safety impact. It includes interpreting and meeting relevant compliance requirements, and developing and implementing proactive measures to exceed them where possible.

Application of the Unit

This unit of competency supports the work of demolition project management staff responsible for regulatory compliance and minimising environmental contamination and public health and safety impacts on structures or installations above 15 metres.

Licensing/Regulatory Information

Licensing, legislative, regulatory or certification requirements apply to demolition work in different States and Territories. Candidates are advised to consult with the relevant regulatory authorities.

Pre-Requisites

Nil

Employability Skills Information

This unit contains employability skills.

Elements and Performance Criteria Pre-Content

Elements describe the essential outcomes of a unit of competency.	Performance criteria describe the required performance needed to demonstrate achievement of the element. Where bold italicised text is used, further information is detailed in the required skills and knowledge and/or the range statement. Assessment of performance is to be consistent with the evidence guide.

Elements and Performance Criteria

1	Assess potential impacts of demolition tasks.	1.1	Environmental and public health and safety compliance requirements for the demolition site and geographic locality are determined.
1.2	Safe work method statements (SWMS) for individual demolition tasks are reviewed and potential impacts on environment are determined.
1.3	Safe work method statements for individual demolition tasks are reviewed and potential impacts on public health and safety are determined.

2	Identify measures to minimise impacts of demolition work on the environment.	2.1	Strategies to minimise impacts on air quality are investigated, selected and incorporated into procedures.
2.2	Strategies to minimise water wastage and impacts on stormwater are investigated, selected and incorporated into procedures.
2.3	Strategies to minimise energy wastage and employ renewable energy technologies are investigated, selected and incorporated into procedures.
2.4	Strategies to minimise material wastage and to ensure safe disposal of hazardous and waste materials are investigated, selected and incorporated into procedures.

3	Identify measures to minimise impacts of demolition work on the public.	3.1	Site containment, exclusion and signage strategies are reviewed and amended to maximise awareness of, and minimise impacts on, the public.
3.2	Pedestrian and traffic management plan for site and site perimeter is reviewed and amended to minimise risks to the public.
3.3	Fall prevention strategies for both personnel and materials are reviewed and amended to minimise risks to site personnel and the public.
3.4	Noise, air pollution and vibration management strategies are reviewed and amended to minimise impact on the public.

4	Brief team and supervise implementation of impact minimisation strategies.	4.1	Strategies for minimising impact of demolition work on the environment and on public health and safety are explained to demolition teams.
4.2	Amended safe work method statements are distributed and questions invited and responded to, as required.
4.3	Implementation of strategies to minimise impact of demolition work on the environment and on public health and safety is monitored and directed.

Required Skills and Knowledge

This section describes the skills and knowledge required for this unit.
Required skills
learning skills to: respond to change, such as differences in environmental and public health and safety standards required by clients use past experience to develop and implement solutions to problems numeracy skills to calculate or estimate: energy use predicted volume of waste oral communication skills to: motivate and direct team members develop and maintain relationships with clients and other relevant personnel reading skills to interpret work specifications writing skills to amend work procedures and safe work method statements
Required knowledge
demolition procedures, techniques and safety requirements demolition site inspection procedures environmental and public health and safety hazards and risks existing or arising on demolition sites, and relevant risk management strategies legislation, regulations, codes and standards relating to environmental and public health and safety on demolition sites plant, tools and equipment required for demolition tasks and: permits and licences required safe operating procedures project management strategies quality management strategies strategies to minimise environmental and public health and safety risks on and around demolition sites team leadership strategies

Evidence Guide

The evidence guide provides advice on assessment and must be read in conjunction with the performance criteria, required skills and knowledge, range statement and the Assessment Guidelines for the Training Package.
Overview of assessment	This unit of competency could be assessed by reviewing the planning of demolition activities to minimise environmental and public health and safety impacts, and observing the supervision of the implementation of planned strategies in the workplace.
Critical aspects for assessment and evidence required to demonstrate competency in this unit	A person should demonstrate the ability to plan and supervise the implementation of strategies to minimise environmental and public health and safety impacts on two different large demolition projects, one of which must involve structures or installations above 15 metres. The evidence shall demonstrate: analysing potential impacts of demolition activities on the environment and on public health and safety interpreting and applying legislation, regulations, codes and standards relating to protecting the environment and public health and safety researching and developing strategies to minimise impacts of demolition activities on the environment and on public health and safety monitoring demolition activities to ensure effective implementation of planned strategies.
Context of and specific resources for assessment	Assessment of this unit: must be in the context of the work environment must meet relevant compliance requirements. Resource implications for assessment include: an induction procedure realistic tasks covering the mandatory task requirements support materials appropriate to activity, including: access to industry information relating to legislation, regulations, codes and standards contractual information and work specifications human resources and plant, tools and equipment appropriate to the tasks.
Method of assessment	Assessment for this unit must verify the practical application of the required skills and knowledge, using a combination of the following methods: direct observation of tasks in real work conditions questioning to confirm the ability to consistently identify and correctly interpret the essential underpinning knowledge required for practical application review of relevant authenticated documentation from third parties, such as existing managers or specialist training staff.
Guidance information for assessment	This unit could be assessed on its own or in combination with other units relevant to the job function. Reasonable adjustments for people with disabilities must be made to assessment processes where required. This could include access to modified equipment and other physical resources, and the provision of appropriate assessment support. Assessment processes and techniques should, as far as is practical, take into account the language, literacy and numeracy capacity of the candidate in relation to the competency being assessed.

Range Statement

The range statement relates to the unit of competency as a whole. It allows for different work environments and situations that may affect performance. Bold italicised wording, if used in the performance criteria, is detailed below. Essential operating conditions that may be present with training and assessment (depending on the work situation, needs of the candidate, accessibility of the item, and local industry and regional contexts) may also be included.
Impacts on the environment must include:	dust energy use excavation hazardous material material disposal sediment storage stormwater quality water use.
Impacts on public health and safety must include:	air pollution relating to: dust fumes smell change or damage to public infrastructure hours of work noise vehicle movements vibration volume of traffic.

Unit Sector(s)

Demolition

Custom Content Section

Not applicable.