Assessment Requirements for MSFKB3011 Plan kitchen and bathroom projects

Release: 1

Assessment Requirements for MSFKB3011 Plan kitchen and bathroom projects

Modification History

Release 1. Supersedes and is not equivalent to MSFKB3001 Identify processed in kitchen and bathroom projects.

Performance Evidence

There must be evidence the candidate has completed the tasks outlined in the elements and performance criteria of this unit, and:

planned and documented the work process for 3 different projects, 1 of which must be a kitchen and 1 of which must be a bathroom.

Knowledge Evidence

There must be evidence the candidate has knowledge of:

typical client requirements and/or potential components of a project brief

roles and responsibilities of all those involved in kitchen and bathroom projects, how these interrelate and the impact on project planning and sequencing:

architects

colour consultants

designers

material and component suppliers

tradespeople:

builders

cabinetmakers

electricians

flooring specialists

glaziers

painters

plumbers / gas fitters

stonemasons

tilers

waterproofers

the overall planning process, potential key stages and sequencing of kitchen and bathroom projects and what each stage involves:

concept design

design specification

planning approval

technical site assessment/site measure

demolition

construction:

services

waterproofing

installation

differences between renovation and new build projects

project planning techniques and required plan inclusions:

sequence of operations

budget

timelines

allocation and delivery of resources

contingencies

features of cabinets and components used in kitchen and bathroom projects, including manufacturing methodologies

supply chains for kitchen and bathroom components and materials.

Assessment Conditions

Skills must have been demonstrated in the workplace or in a simulated environment that reflects workplace conditions and contingencies. The following conditions must be met for this unit:

use of suitable facilities, equipment and resources, including:

project briefs.

Assessors must satisfy the NVR/AQTF mandatory competency requirements for assessors.

Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=0601ab95-583a-4e93-b2d4-cfb27b03ed73