# AHCECR402 Plan the implementation of revegetation works

Release: 1

AHCECR402 Plan the implementation of revegetation works

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 6.0. |

# Application

This unit of competency describes the skills and knowledge required to confirm and assess resources, program works and schedules and prepare a plan for the implementation of revegetation works.

The unit applies to individuals who work in a supervisory role in revegetation works and provide and communicate solutions to a range of predictable and sometimes unpredictable problems. They work autonomously, instruct, and monitor the work of others within a team. They use discretion and judgment in the selection, allocation and use of available resources.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Unit Sector

Ecological Restoration (ECR)

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Carry out preliminary planning activities for implementation of revegetation works | 1.1 Confirm scope, preferences, contract requirements and goals for revegetation works 1.2 Identify statutory obligations and site responsibilities affecting revegetation works 1.3 Conduct site visit to verify the biophysical, environmental and historical conditions 1.4 Identify site health and safety hazards, assess risk and develop controls 1.5 Verify availability, quantity and costs of resources specified in project plan |
| 2. Prepare a staged plan for revegetation works | 2.1 Identify, cost and confirm availability of materials, tools and equipment required for revegetation work 2.2 Assess and resolve site access and establishment difficulties 2.3 Assess sequence of works for site establishment and maintenance 2.4 Consider seasonal factors and impact on sequencing strategy 2.5 Identify habitat development and enhancement requirements for site 2.6 Prepare a program plan and schedule of revegetation works 2.7 Document a staged implementation plan according to workplace procedures |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential for performance in this unit of competency but are not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Reading | Critically analyse scoping documentation, legislation and regulations to identify objectives, resources and compliance requirements and consolidate into programs, schedules and revegetation plans |
| Writing | Prepare, proofread and edit programs, schedules and plans for revegetation works, ensuring clarity of meaning, accuracy and consistency of information |
| Numeracy | Calculate quantities of materials and the respective costs Estimate the time required for equipment, materials and labour, and cost of securing these resources |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| AHCECR402 Plan the implementation of revegetation works | AHCNAR402 Plan the implementation of revegetation works | Changed unit code to reflect new unit sector Changes to Application and Performance Criteria for clarity and brevity Updated Performance Evidence, Knowledge Evidence and Assessment Conditions | Equivalent |

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72