# AHCNRM511 Plan and monitor works projects in catchments and waterways

Release: 1

AHCNRM511 Plan and monitor works projects in catchments and waterways

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 6.0. |

# Application

This unit of competency describes the skills and knowledge required to plan, implement, monitor and review works projects conducted in catchments and waterways. This includes engaging and working with stakeholders and ensuring works meet environmental and project outcomes and priorities.

The unit applies to individuals who are engaged in contract project works in catchments and waterways who take personal responsibility and exercise autonomy in undertaking work. They have accountability for the work of others and analyse, design and communicate solutions to a range of complex problems.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Unit Sector

Natural Resource Management (NRM)

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Inspect and assess catchment and waterways sites for inclusion in a works program | 1.1 Establish the environmental outcomes and priorities of the works program 1.2 Apply workplace health and safety policies and procedures, environmentally sustainable practices and biosecurity measures 1.3 Conduct a site assessment to confirm the physical characteristics and health of catchment and waterways 1.4 Assess the range of operating conditions, hazards and sensitive environments for impact on proposed projects 1.5 Assess heritage and cultural values of sites 1.6 Consult project stakeholders on the scope and purpose of the works program |
| 2. Plan works project | 2.1 Consult with stakeholders to determine project priorities 2.2 Obtain permits, licenses and authorisations 2.3 Determine and source equipment and materials and personnel required for project 2.4 Confirm terms and conditions of project work with project stakeholders 2.5 Prepare plans and specifications for works project 2.6 Complete project documentation and communicate details to stakeholders |
| 3. Monitor works project | 3.1 Establish monitoring program according to works objective 3.2 Establish data benchmarks for evaluating the outcomes of project 3.3 Identify ongoing support required of contractors and project workers 3.4 Provide ongoing support according to identified needs in a timely manner 3.5 Monitor condition of the project site to ensure it is left in an agreed condition 3.6 Report outcomes of monitoring to workplace requirements |
| 4. Review works program | 4.1 Evaluate projects for compliance with agreed outcomes 4.2 Determine projects comply with environmental targets 4.3 Recommend changes to works program to achieve catchment and waterways priorities where non-compliance has been identified 4.4 Use a relational data management system for recording monitoring data and reporting to stakeholders |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential for performance in this unit of competency but are not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Writing | Record outcomes of programs into relational database and reports expressing ideas and exploring complex issues in recommendations, ensuring accurate, succinct and logically constructed text |
| Oral Communication | Establish and maintain effective communications when negotiating and consulting with stakeholders on projects and when providing feedback on project performance |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| AHCNRM511 Plan and monitor works projects in catchments and waterways | AHCNRM506 Plan and monitor works projects in catchments and waterways | Minor changes to Application and Performance Criteria for clarity Updated Performance Evidence, Knowledge Evidence and Assessment Conditions | Not equivalent |

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72

Assessment Requirements for AHCNRM511 Plan and monitor works projects in catchments and waterways

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 6.0. |

# Performance Evidence

An individual demonstrating competency must satisfy all of the elements and performance criteria in this unit.

There must be evidence that the individual has planned and monitored at least one catchment and waterways project, and has:

applied effective consultation techniques to ensure stakeholder contribution to project priorities

researched and determined environmental conditions of project worksites

worked with and supported project stakeholders during project implementation

developed waterway monitoring program that must include:

selected representative water quality monitoring sites

selected macro invertebrate monitoring sites

used data collection guidelines and parameters

specified timelines for monitoring

monitored project to ensure it complied with regulatory requirements

evaluated impact of projects on sustainable catchment management

determined the physical and human resources required for project

determined monitoring procedures sufficient for evaluating and reviewing project

evaluated environmental benefits of works program using workplace techniques and reporting methods

completed reporting requirements according to workplace standards and stakeholders outcomes.

# Knowledge Evidence

An individual must be able to demonstrate the knowledge required to perform the tasks outlined in the elements and performance criteria of this unit. This includes knowledge of:

physical characteristics and indicators of health of waterways and catchments

wetland and floodplain processes and function, including:

factors that influence stream flow

stream dynamics

stream formation

eutrophication

impacts of land use on waterways

indicators of catchment health, including:

pest plant and animal infestations

vegetation decline

soil erosion

stream bank erosion

water quality decline

water quality parameters, including:

physical and chemical properties of water

biological indicators of water quality

project planning processes

consulting and negotiating with stakeholders, including:

investors

partners

interest groups

agencies

permits and licences required for on-ground works.

# Assessment Conditions

Assessment of the skills in this unit of competency must take place under the following conditions:

physical conditions:

skills must be demonstrated in an environment that accurately represents workplace conditions

specifications:

workplace policies and procedures for monitoring and reporting

legislation and regulations for water catchment management

relationships:

stakeholders

work team and/or contractors

timeframes:

according to time specified in program for supporting project.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72