# AHCPER315 Coordinate community projects

Release: 1

AHCPER315 Coordinate community projects

# Modification History

| Release | TP Version | Comment |
| --- | --- | --- |
| 1 | AHCv1.0 | Initial release |

# Application

This unit of competency describes the skills and knowledge required to coordinate small-scale community projects and small groups of people working on a permaculture-related project.

All work is carried out to comply with workplace procedures.

This unit applies to individuals who take responsibility for their own work and for the quality of the work of others. They use discretion and judgement in the selection, allocation and use of available resources.

No occupational licensing, legislative or certification requirements are known to apply to this unit at the time of publication.

# Pre-requisite Unit

Nil.

# Unit Sector

Permaculture (PER)

# Elements and Performance Criteria

| Element | Performance criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Prepare for community project | 1.1 Clarify requirements of the community project after community consultation and design 1.2 Identify personnel, equipment and material resource requirements appropriate to the scope of the project 1.3 Identify on-site, off-site, purchased, traded or scavenged resources 1.4 Identify and document the order of activities and allocate time to carry them out 1.5 Identify the environmental implications of proposed community projects and assess likely outcomes 1.6 Identify work health and safety hazards, assess risks, implement controls and take appropriate actions 1.7 Select, use and maintain personal protective equipment appropriately (PPE) |
| 2. Organise resources | 2.1 Acquire materials, equipment and resources 2.2 Apply for external agency permits in the correct order where required 2.3 Notify affected parties of works to be undertaken where required 2.4 Organise delivery of materials, equipment and resources to site 2.5 Organise personnel to be on site when they are required |
| 3. Coordinate and report on activities | 3.1 Coordinate all resources to suit the scope of the project and the project plan 3.2 Direct personnel in activities for each period of work 3.3 Monitor personnel, activities, timelines and resource usage and document 3.4 Recognise contingency situations and take corrective action as appropriate 3.5 Select and train teams to take over the running of the project to ensure the long-term survival of the project, if required 3.6 Write a project report to inform the community and other stakeholders |

# Foundation Skills

Foundation Skills essential to performance are explicit in the performance criteria of this unit of competency.

# Range of Conditions

# Unit Mapping Information

New unit - equivalent to QLD843COM15B.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72