# AHCPER503 Develop a strategic plan for a permaculture project or enterprise

Release: 1

AHCPER503 Develop a strategic plan for a permaculture project or enterprise

# Modification History

| Release | TP Version | Comment |
| --- | --- | --- |
| 1 | AHCv1.0 | Initial release |

# Application

This unit of competency describes the skills and knowledge required to develop a strategic plan for a permaculture project or enterprise. It requires the ability to prepare a strategic plan brief, research and analyse planning information, develop strategic plan stages, document a strategic plan, and review a strategic plan against desired outcomes. Developing a strategic plan for a permaculture project requires knowledge of permaculture principles and practices, climate change and peak oil impacts, sustainable community development practices, research methods and strategic planning methodologies.

All work is carried out to comply with workplace procedures.

This unit applies to individuals who analyse information and exercise judgement to complete a range of advanced skilled activities and demonstrate deep knowledge in a specific technical area. They have accountability for the work of others and analyse, design and communicate solutions to a range of complex problems.

No occupational licensing, legislative or certification requirements are known to apply to this unit at the time of publication.

# Pre-requisite Unit

Nil.

# Unit Sector

Permaculture (PER)

# Elements and Performance Criteria

| Element | Performance criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Develop a strategic plan brief for a permaculture project or enterprise | 1.1 Evaluate the current context of the permaculture project or enterprise 1.2 Determine core values of the project or enterprise 1.3 Define project vision statement, aims and objectives 1.4 Establish project or enterprise goals in consultation with stakeholders 1.5 Evaluate strategic plan values, goals and vision statement with respect to permaculture principles and ethics 1.6 Document strategic planning brief 1.7 Develop protocols on cultural respect and sensitivity 1.8 Review and revise strategic plan brief at appropriate project development intervals |
| 2. Research and analyse strategic planning information | 2.1 Determine information needed for strategic plan with reference to plan brief 2.2 Identify key elements and themes 2.3 Determine research subjects 2.4 Compose research plan and methodologies 2.5 Review local, state and national government legal and planning acts and codes relevant to project or enterprise 2.6 Review and revise strategic plan brief in relation to research findings |
| 3. Identify strategic planning stages | 3.1 Identify strategies required to achieve planning goals in consultation with relevant parties 3.2 Determine action plans required to execute strategies 3.3 Order strategies and action plans into a series of strategic planning stages 3.4 Determine planning benchmarks for future stage completion review 3.5 Review and revise plan brief with reference to strategic planning stages |
| 4. Document and distribute strategic plan | 4.1 Produce a clear, concise and consistently formatted written strategic planning document 4.2 Distribute strategic plan to all relevant parties to ensure effective communication of project or enterprise planning 4.3 Take feedback on plan documentation and review and revise documentation as required |
| 5. Review strategic plan | 5.1 Determine mechanism for evaluation of strategic plan 5.2 Determine timeframes for evaluation 5.3 Evaluate with reference to permaculture principles and practices 5.4 Evaluate feedback from all relevant parties on implementation issues and outcomes 5.5 Identify problems and revise as required |

# Foundation Skills

Foundation Skills essential to performance are explicit in the performance criteria of this unit of competency.

# Range of Conditions

# Unit Mapping Information

New unit - equivalent to QLD125PLA03C.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72

Assessment Requirements for AHCPER503 Develop a strategic plan for a permaculture project or enterprise

# Modification History

| Release | TP Version | Comment |
| --- | --- | --- |
| 1 | AHCv1.0 | Initial release |

# Performance Evidence

The candidate must be assessed on their ability to integrate and apply the performance requirements of this unit in a workplace setting. Performance must be demonstrated consistently over time and in a suitable range of contexts.

The candidate must provide evidence that they can:

develop a strategic plan brief

acquire project resources

undertake stakeholder consultation

document a strategic plan

evaluate the vision statement

interpret feedback on the strategic plan

demonstrate group leadership

# Knowledge Evidence

The candidate must demonstrate knowledge of:

permaculture principles, ethics and practices

The two main summaries of permaculture principles are found in Bill Mollison and Reny Mia Slay Introduction to Permaculture (1991) and David Holmgren Permaculture: Principles & Pathways Beyond Sustainability (2002)

sustainable agriculture

garden agriculture

sustainable horticulture

sustainable aquaculture

soil restoration

bush regeneration

biodiversity regeneration

sustainable community development

sustainable project and enterprise development

bioregional development

relocalisation

sustainable design

sustainability education

earth care

people care

return of surpluses and setting limits to growth

permaculture values

environmental restoration

sustainable food production

sustainability education

environmentally sustainable human habitation

sustainable community development

sustainable community transition

right livelihood

social justice

ecological economics

universal human rights

cultural recognition

permaculture projects or enterprises

community gardens

permaculture workshops, training and education

sustainable agricultural systems

urban permaculture systems

community sustainable transition initiatives

climate change initiatives

conservation organisations

sustainability not-for-profits, NGOs, businesses, companies, trusts and incorporated community associations

permaculture design consultancies

permaculture system implementation services

alternative community finance and economic systems

permaculture information and communication services

strategic planning

vision statement

statements of where project or enterprise would like to be in future

imagined futures

statements of possible futures for world outside of project

project or enterprise goals

environmental targets

community development targets

food production

design criteria

happiness indicators

sustainability indicators

strategies

human resource management

financial planning

purchases and acquisitions

cost cutting

income generation

promotion and marketing

organisational restructuring

project or enterprise start up

mentoring and education

new project or enterprise initiatives

political lobbying

grant applications

community consultation

research and development

action plans - sequences of smaller steps necessary to achieve strategies

timelines

benchmarks, such as

verifiable stage completion criteria

numerical indicators

qualitative indicators

observable outcomes

community development

project management

feasibility study methodology

contract law

budgetary frameworks

# Assessment Conditions

Assessors must satisfy current standards for RTOs. Assessors must also have a nationally accredited Diploma of Permaculture. Completion of a Permaculture Design Course (PDC) or non-accredited Permaculture Diploma is not sufficient at this level.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72