# AHCPER517 Plan and supervise the implementation of permaculture project works

Release: 1

AHCPER517 Plan and supervise the implementation of permaculture project works

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 9.0. |

# Application

This unit of competency describes the skills and knowledge required to scope, plan and implement a permaculture project, including identifying and preparing site health and safety procedures, scoping and planning the equipment and materials required, scheduling and sequencing the work, organising and supervising project works, and monitoring quality for a permaculture project.

The unit applies to individuals who analyse information and exercise judgement to complete a range of advanced skilled activities and demonstrate deep knowledge in a specific technical area. They take accountability for the work of others and analyse, design and communicate solutions to a range of complex problems.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Unit Sector

Permaculture (PER)

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Prepare for permaculture project works | 1.1 Confirm and verify client preferences and contract requirements for project 1.2 Determine scope of works 1.3 Identify specific statutory obligations 1.4 Inspect site and verify site conditions and characteristics against permaculture project plan 1.5 Investigate, assess and resolve technical challenges identified from site visit 1.6 Review scope of works and contract requirements according to permaculture and organic principles 1.7 Prepare site-specific procedures for health and safety and environmental hazards according to workplace procedures and statutory obligations |
| 2. Investigate resource issues associated with works | 2.1 Verify availability, quantity and costs of materials specified in project plan and schedules 2.2 Identify and cost material resources, tools and equipment required for works 2.3 Confirm availability with suppliers, contractors and stakeholders 2.4 Confirm site access and establishment issues and plan for environmental impact |
| 3. Prepare a project works plan | 3.1 Prepare a statement of works for project 3.2 Prepare a safety plan for project work 3.3 Specify tools and materials and their source for required project works 3.4 Prepare a staged sequential program of works according to scheduled timelines 3.5 Prepare specifications for project resources and works outcomes 3.6 Verify program of works complies with industry standards and practices 3.7 Determine the establishment and maintenance periods for works 3.8 Incorporate seasonal factors and impact in staging strategy 3.9 Develop and prepare a works plan according to workplace and industry standards |
| 4. Implement project works plan | 4.1 Supervise project work activity 4.2 Coordinate delivery of materials and equipment according to workplace procedures 4.3 Assemble and brief site-specific human resources 4.4 Undertake health and safety briefings according to project health and safety plan 4.5 Implement project works according to sequence, scheduled timelines and specifications 4.6 Monitor, verify and resolve quality issues for substandard works 4.7 Resolve substandard work according to project plan and workplace procedures 4.8 Monitor and resolve environmental impact of project works according to project plan and environmental procedures |
| 5. Inspect and finalise completed project works | 5.1 Inspect and assess works against project outcomes and specifications with client 5.2 Resolve substandard work identified during works inspection 5.3 Confirm completion of works with client 5.4 Close project according to workplace procedures |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential for performance in this unit of competency but are not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Writing | Develop plans and procedural texts for permaculture activities using clear and industry specific language in order to convey explicit information, requirements and recommendations Prepare documentation that expresses ideas, explores complex issues and is constructed logically, succinctly and accurately |
| Oral communication | Establish and maintain complex and effective communications during negotiations, discussion and confirmation of works with stakeholders, demonstrating a depth of understanding of complex oral texts |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| AHCPER517 Plan and supervise the implementation of permaculture project works | AHCPER505 Plan and supervise the implementation of permaculture project works | Changes to Application for clarity Split Element and reviewed sequencing of Performance Criteria for clarity Changes to Performance Evidence, Knowledge Evidence and Assessment Conditions for clarity Addition of Foundation Skills | Not equivalent |

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72

Assessment Requirements for AHCPER517 Plan and supervise the implementation of permaculture project works

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 9.0. |

# Performance Evidence

An individual demonstrating competency must satisfy all of the elements and performance criteria in this unit.

There must be evidence that the individual has, planned and supervised the implementation of a permaculture project and has:

determined and reviewed project scope of work

inspected site and verified site characteristics against project plan, including:

biophysical

environmental

historical

assessed and resolved site technical challenges associated with implementation of permaculture works

prepared schedules for implementation of permaculture works

prepared a staged permaculture works plan

prepared site-specific health, safety and environmental procedures

engaged and briefed human resources on works and health and safety

supervised permaculture project works and monitored and rectified quality issues

inspected and finalised project works with client.

# Knowledge Evidence

An individual must be able to demonstrate the knowledge required to perform the tasks outlined in the elements and performance criteria of this unit. This includes knowledge of:

permaculture and organic principles and practices

types and characteristics of permaculture project works, including:

food and community gardens

urban and rural permaculture systems

aquaculture, horticulture, forest systems

agriculture grazing and pasture systems

integrated food, fibre and energy systems

permaculture infrastructure requirements

sustainable soil management

water management and distribution

natural ecosystem conservation and regeneration

permaculture design techniques, including zone and sector planning

physical and biophysical factors of a site, including:

location and boundaries of site

environmental considerations

site access issues

utility service

adjacent landholder considerations

security issues

climatic conditions, including rainfall, humidity, wind and sunlight intensity

soil types and characteristics, including nutrients and deficiencies

property characteristics, including slope, aspect, natural and artificial watercourses, outcrops of rock, presence of significant vegetation

weeds and existing plants

feral or indigenous animals and their management

practical understanding of the environmental issues associated with undertaking permaculture works, including:

use of materials that come from sustainable sources

duty of care in conserving sites natural values

work practices

the use and movement of machinery, storage of materials, removal of weeds and movement of soil and other materials into, across and beyond the site

principles of ecology, including specific plant and animal relationships and habitat requirements

statutory compliance and obligations, including:

compliance with legislation, ordinances, regulations or by-laws relating to the works or the work site

site responsibilities, including OHS, industrial relations and equal opportunity and employment

site evaluation techniques, including methods of analysing soils, waterways and their condition

soil conservation, erosion control and enhancement techniques and their advantages and disadvantages in reference to specific sites and habitats

selection and use of machinery and tools

work health and safety hazards, risks and controls

contract documentation, including specifications, plans of permaculture works, services, supplies and surveyors documents

planning and documenting project works, including:

scope of works

statement of works

works breakdown into tasks

scheduling and timelines

quality assurance in project works, including interpretation and evaluation of specifications.

# Assessment Conditions

Assessment of the skills in this unit of competency must take place under the following conditions:

physical conditions:

skills must be demonstrated for a permaculture system project or an environment that accurately represents workplace conditions

resources, equipment and materials:

tools, equipment and resources of permaculture works

personal protective equipment

materials for project

specifications:

workplace policies, procedures, processes

manufacturer operating instructions for equipment and machinery

safety data sheets

project plans and specifications

specific legislation and industry codes of practice

relationships:

clients

work team and other stakeholders

timeframes:

according to times specified in project plan.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72