# AHCPGD508 Plan the restoration of parks and gardens

Release: 1

AHCPGD508 Plan the restoration of parks and gardens

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 7.0. |

# Application

This unit of competency describes the skills and knowledge required to plan the restoration of parks and gardens of historical or cultural significance, develop a comprehensive restoration program of works and develop a relevant site plan, specifications and work procedures.

The unit applies to individuals who apply specialist skills and knowledge to planning the restoration of parks and gardens, take personal responsibility and exercise autonomy in undertaking complex work. They analyse and synthesise information, and analyse, design and communicate solutions to sometimes complex problems.

All work is carried out to comply with workplace procedures, health and safety in the workplace requirements, legislative and regulatory requirements, and sustainability and biosecurity practices.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Unit Sector

Parks and Gardens (PGD)

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Carry out preliminary planning activities for restoration works | 1.1 Discuss and clarify client preferences and requirements for park or garden 1.2 Assess site for biophysical factors, historical and cultural attributes, services and site modifications 1.3 Research legal requirements and local by-laws and restrictions that may affect plan for restoration works 1.4 Identify and minimise environmental impact of planned restoration works according to environmental and biosecurity legislation, regulations and workplace procedures, and, if necessary, report to relevant personnel for further research 1.5 Develop concept plan that reflects client preferences and requirements and takes into account heritage issues, site factors and any identified environmental requirements 1.6 Present concept plan to client for discussion and approval 1.7 Consult with other professionals to assist in research and planning of restoration works to meet legislative requirements |
| 2. Determine requirements of restoration works | 2.1 Identify plants appropriate to site, consistent with agreed concept plan and original design philosophy, taking into consideration historical and cultural values 2.2 Calculate and cost quantity of plants and confirm availability and genetic integrity with suppliers 2.3 Select restoration procedures consistent with agreed concept plan, and account for characteristics of available plant materials, resources and equipment and environmental factors affecting the success of the restoration works 2.4 Include maintenance of softscape and hardscape components of park or garden 2.5 Identify and cost resources, tools, equipment and machinery required for planting and ongoing maintenance of restoration works and confirm availability with suppliers, contractors and appropriate personnel 2.6 Identify hazards and assess risks associated with work activities, and implement control measures according to workplace health and safety procedures 2.7 Outline staged implementation and development, where appropriate, including providing access for future works as required by client and site requirements 2.8 Determine timelines for preparations, planting and maintenance, taking into account the needs of restoration species, softscape and hardscape components, site conditions, and other relevant planning requirements |
| 3. Prepare and document the restoration plan and specifications | 3.1 Prepare detailed plan, specifications and quotation based on horticultural conventions, original design philosophy and requirements of restoration works, and present to client for acceptance 3.2 Produce scaled site plan which can be readily interpreted and understood by on-site personnel 3.3 Develop and document detailed on-site procedures and schedules required for restoration and ongoing maintenance of park or garden |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential for performance in this unit of competency but are not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Oral communication | Initiate discussions with client and other professionals, using clear language and standard industry terminology to discuss restoration preferences and requirements, and legal and legislative requirements |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| AHCPGD508 Plan the restoration of parks and gardens | AHCPGD502 Plan the restoration of parks and gardens | Minor changes to application Minor changes to performance criteria Foundation skills added Assessment requirements updated | Equivalent |

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72

Assessment Requirements for AHCPGD508 Plan the restoration of parks and gardens

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 7.0. |

# Performance Evidence

An individual demonstrating competency must satisfy all of the elements and performance criteria in this unit.

There must be evidence that the individual has planned the restoration of parks and gardens on at least one occasion and has:

consulted with clients

determined requirements of the restoration work

complied with legislative requirements

researched and evaluated information

applied relevant workplace health and safety and environmental and biosecurity legislation, regulations and workplace procedures

calculated the cost and spatial and logistical requirements of components of the restoration works

selected restoration procedures that are consistent with the agreed concept plan, appropriate to the site and account for historical and cultural values, available resources and relevant environmental factors

prepared and documented the restoration plan and specifications.

# Knowledge Evidence

An individual must be able to demonstrate the knowledge required to perform the tasks outlined in the elements and performance criteria of this unit. This includes knowledge of:

principles and practices of park and garden restoration, including:

construction procedures, plant selection and cultural practices for historically or culturally significant parks and gardens

growth habits and cultural requirements of specific plants under a range of soil and environmental conditions

historic parks and gardens management principles and guidelines

legislation and regulations relating to heritage sites and restoration works

maintenance requirements and practices for specific plants prior to and after initial establishment

principles of the Australian Natural Heritage Charter, the Draft Guidelines for the Protection, Management and Use of Aboriginal and Torres Strait Islander Cultural Heritage Places and the Burra Charter

role of project briefs and client consultation processes in planning restoration works

site evaluation techniques, including methods of analysing the condition of soils, plants and waterways for restoration activities

workplace health and safety and environmental and biosecurity legislation, regulations and workplace procedures relevant to planning the restoration of parks and gardens.

# Assessment Conditions

Assessment of the skills in this unit of competency must take place under the following conditions:

physical conditions:

a workplace setting or an environment that accurately represent workplace conditions

resources:

computer software and hardware relevant to planning the restoration of parks and gardens

specifications:

workplace health and safety and environmental and biosecurity legislation, regulations and workplace procedures relevant to planning the restoration of parks and gardens

legislative and regulatory requirements relevant to planning the restoration of parks and gardens

Australian Natural Heritage Charter and the Draft Guidelines for the Protection, Management and Use of Aboriginal and Torres Strait Islander Cultural Heritage Places and the Burra Charter

relationships:

clients, other professionals

timeframes:

according to job requirements.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72