# AHCSAW503 Plan conservation earthworks

Release: 2

AHCSAW503 Plan conservation earthworks

# Modification History

| Release | Comments |
| --- | --- |
| Release 2 | This version released with AHC Agriculture, Horticulture and Conservation and Land Management Training Package Version 6.0. |

# Application

This unit of competency describes the skills and knowledge required to develop a conservation earthworks plan to control runoff to prevent soil erosion, safely store and distribute water, and rehabilitate eroded or disturbed areas.

The unit applies to individuals who take personal responsibility and exercise autonomy in undertaking complex work. This includes analysing, designing and communicating solutions to sometimes complex problems.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Unit Sector

Soil and Water Conservation (SAW)

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Establish client needs | 1.1 Consult with landholder on proposed land use 1.2 Review and discuss the catchment characteristics for proposed land use 1.3 Explain to landholder impact of legislation and policies on project 1.4 Determine budget constraints for project 1.5 Discuss possible strategies with landholder 1.6 Seek agreement for proposed land use and strategy from landholder according to workplace procedures |
| 2. Develop the strategy to utilise earthworks | 2.1 Check titles and maps to confirm property ownership 2.2 Determine profile of catchment from survey and aerial photographs 2.3 Develop earthworks concept consistent with industry principles and selection criteria 2.4 Establish final water disposal points according to proposed strategy 2.5 Survey location of proposed earthworks and structures on site, and discuss with landholder 2.6 Document preferred strategy for future reference |
| 3. Prepare a detailed works plan | 3.1 Assess and select earthworks, structures or measures according to proposed land use and industry standards 3.2 Cost project and develop schedule for plan 3.3 Communicate design of structures and specifications to qualified designer 3.4 Prepare and present a conservation earthworks plan and documentation according to workplace procedures and industry standards |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential for performance in this unit of competency but are not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Reading | Organise, evaluate and analyse ideas and information from land use documents, catchment characteristics, titles and maps to determine requirements and ensure compliance with legislation and industry standards |
| Writing | Demonstrate sophisticated writing skills by selecting appropriate conventions and stylistic devices to express precise meaning in plans and strategies Prepare documentation and specifications for plans and designs, expressing ideas, exploring complex design issues and constructing the documents accurately and succinctly to industry standards |
| Numeracy | Use highly developed numeracy skills to interpret complex design ideas, and perform calculations with precision and accuracy for inclusion in conservation earthworks plans |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| AHCSAW503 Plan conservation earthworks Release 2 | AHCSAW503 Plan conservation earthworks Release 1 | Minor changes to Application and Performance Criteria for clarity Foundation Skills added Updated Performance Evidence, Knowledge Evidence and Assessment Conditions | Equivalent |

# Links

Companion Volumes, including Implementation Guides, are available at VETNet: - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=c6399549-9c62-4a5e-bf1a-524b2322cf72