# BSBATSIM417 Implement organisational plans

Release: 1

BSBATSIM417 Implement organisational plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 1.0. |

# Application

This unit describes the skills and knowledge required to guide the implementation of organisational plans.

It applies to individuals who are responsible for monitoring and guiding activities of Aboriginal and Torres Strait Islander organisations.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Regulation, Licensing and Risk – ATSI Governance

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1 Secure resources and funding to implement organisational plans | 1.1 Review organisational plan to identify required resources and funding sources 1.2 Identify possible partnership arrangements 1.3 Follow organisation’s policies, practices and procedures to obtain resources and funding to implement plans |
| 2 Oversee implementation of organisational plans | 2.1 Establish a plan for implementation 2.2 Identify roles and responsibilities of board members in implementation plan 2.3 Identify key performance indicators (KPIs) for plan implementation and use to monitor progress 2.4 Establish internal reporting strategies to inform board members of implementation progress 2.5 Undertake contingency planning in consultation with key stakeholders as required 2.6 Ensure procedures are in place to document planning and implementation outcomes |
| 3 Monitor, review and evaluate implementation | 3.1 Analyse implementation progress reports 3.2 Develop strategies to address changing situations when necessary 3.3 Make appropriate implementation decisions as required, including changes to plan 3.4 Evaluate implementation of organisational plan |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the performance criteria that are required for competent performance.

| Skill | Performance Criteria | Description |
| --- | --- | --- |
| Reading | 1.1-1.3, 2.2, 2.3, 3.1, 3.4 | Gathers, interprets and analyses a variety of textual information from a range of sources and identifies relevant and key information |
| Writing | 2.1, 2.4-2.6, 3.2, 3.3 | Uses clear vocabulary, grammatical structures and conventions appropriate for target audience when completing and updating workplace documentation |
| Oral Communication | 2.5 | Participates in verbal exchanges using clear language, suitable syntax and tone to address and disseminate information to a variety of individuals Uses active listening and questioning to convey and clarify information |
| Numeracy | 1.1, 2.1, 2.3 | Interprets numerical information and applies mathematical calculations to determine resources, KPIs and time requirements |
| Navigate the world of work | 1.3 | Monitors adherence to organisational policies and procedures and considers own role in terms of its contribution to broader goals of work environment |
| Get the work done | 1.1, 1.2, 2.1-2.5, 3.1-3.4 | Applies formal processes when planning more complex tasks, producing plans with logically sequenced steps, reflecting an awareness of time, resource constraints and the needs of others In more complex non-routine situations, uses formal decision-making process with support, setting or clarifying goals, gathering information and identifying and evaluating best options against predetermined criteria Applies formal problem-solving processes, breaking complex issues into manageable parts and identifying and evaluating several options for action Understands and explicitly applies some basic principles of analytical and lateral thinking |

# Range of Conditions

This section specifies different work environments and conditions that may affect performance. Essential operating conditions that may be present (depending on the work situation, needs of the candidate, accessibility of the item, and local industry and regional contexts) are included.

| Plan for implementation must include: | key tasks and activities key milestones and deliverables, such as results and KPIs key stakeholders responsible person resources required timeline reporting requirements |
| --- | --- |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| BSBATSIM417 Implement organisational plans | BSBATSIM417A Implement organisational plans | Updated to meet Standards for Training Packages | Equivalent unit |

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10

Assessment Requirements for BSBATSIM417 Implement organisational plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 1.0. |

# Performance Evidence

Evidence of the ability to:

develop an implementation plan that clearly identifies key activities, personnel, outcomes, resource requirements and timelines

establish strategies to monitor, review and evaluate implementation

solve implementation problems that may affect the plan.

Note: If a specific volume or frequency is not stated, then evidence must be provided at least once.

# Knowledge Evidence

To complete the unit requirements safely and effectively, the individual must:

explain concept of community control of organisations and how it may impact organisational planning

outline contingency planning strategies

describe cultural context in which Aboriginal and Torres Strait Islander boards operate, including their role in upholding traditional and cultural values, and how that may affect the implementation of organisational plans

identify geographic, social, economic and political contexts in which particular organisations operate and how these may impact the viability of organisational plans

outline the key elements of implementation plans

list legislation and funding body requirements that may influence planning decisions

explain methods for monitoring and reporting plan implementation

outline organisational policies, practices and procedures relevant to development of organisational plans

identify possible partnership arrangements with other organisations to achieve organisational objectives

outline protocols and cultural responsibilities relevant to development of organisational plans

describe roles and responsibilities of board members

identify sources of funding and other key resources relevant to implementing organisational plans.

# Assessment Conditions

Assessment must be conducted in a safe environment where evidence gathered demonstrates consistent performance of typical activities experienced in the regulation, licensing and risk – ATSI governance field of work and include access to:

participation on an actual or simulated board

examples of relevant planning implementation documents

examples of issues that affect planning implementation.

Assessors must satisfy NVR/AQTF assessor requirements.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10