# BSBLEG425 Apply principles of legal project management

Release: 1

BSBLEG425 Apply principles of legal project management

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Application

This unit describes the skills and knowledge required to apply project management skills in a legal context to assist in the delivery of project to time and cost requirements.

The unit applies to those who have a broad knowledge of project management who contribute well-developed skills to creating solutions to unpredictable problems. They may have responsibility to provide guidance or to delegate aspects of these tasks to others.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Technical Skills – Legal Services

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Plan project | 1.1 Identify project scope according to client instructions 1.2 Identify project resources 1.3 Identify project risk and mitigation measures 1.4 Confirm deliverable with management according to organisational policy 1.5 Develop project plan according to client and organisational requirements |
| 2. Execute project | 2.1 Support in developing deliverable according to client and organisational requirements 2.2 Assist in monitoring project progress against project objectives 2.3 Contribute to rectifying contingencies according to organisational policies and task requirements |
| 3. Maintain project | 3.1 Seek feedback from relevant stakeholders on project management processes to inform lessons learned 3.2 Analyse and amend processes according to feedback 3.3 Record and action feedback as required according to organisational policy and procedures |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Learning | Evaluates effectiveness of plans and results to inform improvement decisions |
| Reading | Extracts and analyses relevant information from texts of varying complexity |
| Writing | Develops a range of documents using structure and vocabulary appropriate to audience, context and purpose |
| Teamwork | Collaborates with others to achieve joint outcomes, playing an active role in facilitating effective group interaction |
| Initiative and enterprise | Adheres to legislative and organisational requirements |
| Planning and organising | Determines job sequence and works logically and systematically to undertake defined tasks |
| Technology | Uses familiar digital technologies and systems to access information, prepare information and support projects |

# Unit Mapping Information

No equivalent unit. New unit.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10

Assessment Requirements for BSBLEG425 Apply principles of legal project management

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

apply project management principles to at least three legal projects.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

legislation and regulations relevant to legal project management

techniques to identify and document client expectations

legal project risks and mitigation techniques

organisational policies and procedures for legal project management

monitoring processes to track project delivery

methods to obtain feedback for identifying lessons learned from relevant personnel.

# Assessment Conditions

Skills in this unit must be demonstrated in a workplace or simulated environment where the conditions are typical of those in a working environment in this industry.

This includes access to:

relevant legislation and regulations relevant to legal project management

organisational policies and procedures for legal project management

relevant software for legal project management.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10