# BSBOPS502 Manage business operational plans

Release: 1

BSBOPS502 Manage business operational plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Application

This unit describes the skills and knowledge required to develop and monitor the implementation of operational plans to support efficient and effective workplace practices and organisational productivity and profitability.

The unit applies to individuals who manage the work of others and operate within the parameters of a broader strategic and/or business plans.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Business Competence – Business Operations

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Establish operational plan | 1.1 Research, analyse and document resource requirements 1.2 Develop operational plan in consultation with, and with approval from, relevant stakeholders 1.3 Develop contingencies for operational plan 1.4 Explain plan to relevant work teams |
| 2. Manage resource acquisition | 2.1 Confirm that employees are recruited and inducted according to the organisation’s human resources management policies, practices and procedures 2.2 Confirm that physical resources and services are acquired according to the organisation’s policies, practices and procedures 2.3 Identify and incorporate requirements for intellectual property rights and responsibilities related to acquisition of resources |
| 3. Monitor and review operational performance | 3.1 Assess progress of operational plan in achieving profit and productivity plans and targets 3.2 Identify areas of under-performance, recommend solutions and rectify the situation 3.3 Plan and implement relevant processes for ongoing monitoring and confirm that support is provided for individuals and teams 3.4 Negotiate recommendations for variations to operational plans and gain approval from designated persons |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the performance criteria that are required for competent performance.

| Skill | Description |
| --- | --- |
| Reading | Gathers, interprets and analyses workplace documentation to determine requirements for the operational plan |
| Writing | Develops and documents a range of detailed texts relating to the management of an operational plan according to organisational requirements |
| Oral communication | Presents information to a range of audiences using appropriate register, vocabulary and paralinguistic features Listens and comprehends information from a variety of spoken exchanges with clients, co-workers and other stakeholders |
| Numeracy | Selects and uses mathematical problem-solving strategies to organise resource requirements, performance benchmarks and financial viability of the operational plan |
| Enterprise and initiative | Monitors adherence to organisational policies, procedures and considers own role in terms of its contribution to broader goals of the work environment |
| Teamwork | Collaborates with others to achieve joint outcomes, playing an active role in facilitating effective group interaction, influencing direction and taking a leadership role on occasion |
| Planning and organising | Takes responsibility for developing and implementing systems and processes to achieve organisational objectives, seeking advice, feedback and support as required to assist in the development and planning phase Sequences and schedules complex activities, monitors implementation, and manages relevant communication |
| Problem solving | Uses systematic analytical processes to aid decision making, identify potential problems and generate contingency plans or solutions |
| Technology | Demonstrates awareness of the importance of data security in a digital environment |

# Unit Mapping Information

Supersedes and is equivalent to BSBMGT517 Manage operational plan.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10

Assessment Requirements for BSBOPS502 Manage business operational plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

manage an operational plan for at least one business or work area.

In the course of the above, the candidate must:

develop and implement an operational plan using a variety of information sources and consultation including:

resource requirements

key performance indicators

monitoring processes

contingency plans

communicate with stakeholders to explain the plan and supporting information, seek approvals, negotiate variations and engage work teams

confirm existence of relevant strategies, including strategies relating to:

recruiting, inducting and developing personnel

acquiring physical resources and services

protecting intellectual property

making variations to the plan

monitoring and documenting performance.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

stakeholders involved in development and management of operations plan including escalation points, colleagues and specialist resource managers

key information sources for proposal development and presentation including resource requirement specialists

consultation processes

content of operational plans, including:

procurement processes

employee recruitment and induction strategies

physical resource and service acquisition strategies

key indicators of organisational performance

budget and actual financial relating to profit and productivity

methods for preparing operational plans and contingency plans

role of an operational plan in achieving an organisation’s objectives

procedures and records associated with documenting performance

approaches for developing key performance indicators to meet business objectives

legislative and regulatory framework relating to the development and implementation of operational plan of the organisation, including:

fair trading laws

work health and safety

organisational policies, practices and procedures that relate to the operational plan.

# Assessment Conditions

Skills in this unit must be demonstrated in a workplace or simulated environment where the conditions are typical of those in a working environment in this industry.

This includes access to:

legislation and regulations relevant to operational plans

workplace documentation and resources relevant to performance evidence.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10