# BSBPMG409 Apply project scope management techniques

Release: 1

BSBPMG409 Apply project scope management techniques

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 1.0. |

# Application

This unit describes the skills and knowledge required to contribute to the control of a project’s scope by assisting with identifying its objectives, deliverables, constraints, assumptions and outcomes; and by applying controls once the project has commenced.

It applies to individuals who are project practitioners working in a project support role.

No licensing, legislative, regulatory or certification requirements apply to this unit at the time of publication.

# Unit Sector

Management and Leadership – Project Management

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Contribute to defining project scope | 1.1 Review project initiation documentation and assist in identifying project objectives and requirements 1.2 Contribute to identifying project deliverables 1.3 Contribute to identifying measurable outcomes to enable evaluation of project performance 1.4 Contribute to developing and documenting the scope management plan 1.5 Assist in obtaining agreement to scope from relevant project authority |
| 2. Apply project scope controls | 2.1 Undertake work according to agreed project scope management plan and by using established change control procedures and performance measurement procedures 2.2 Communicate instances of non-compliance with overall scope to the project manager and other team members |
| 3. Contribute to review of scope controls | 3.1 Measure progress to determine potential, perceived and actual scope changes 3.2 Appropriately report scope changes 3.3 Assist in review of project outcomes to determine effectiveness of initial and subsequent scope management approaches |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the performance criteria that are required for competent performance.

| Skill | Performance Criteria | Description |
| --- | --- | --- |
| Reading | 1.1 | Interprets and analyses complex texts |
| Writing | 1.4, 1.5, 3.2 | Develops and amends plans and associated documentation using appropriate organisational formats and vocabulary |
| Oral Communication | 1.2-1.5, 2.2 | Interacts effectively in verbal exchanges, using clear language to convey information, and active listening and questioning to clarify understanding |
| Numeracy | 1.3, 3.1 | Selects and applies a range of mathematical and problem-solving strategies to develop timelines and monitor progress |
| Interact with others | 1.2-1.5, 2.2 | Uses appropriate communication practices in a range of work contexts Collaborates and cooperates with others to achieve shared goals |
| Get the work done | 2.1, 3.1, 3.2, 3.3 | Plans and organises tasks required to monitor and report on project implementation Analyses outcomes to identify future improvements |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| BSBPMG409 Apply project scope management techniques | BSBPMG409A Apply project scope-management | Updated to meet Standards for Training Packages | Equivalent unit |

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10

Assessment Requirements for BSBPMG409 Apply project scope management techniques

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 1.0. |

# Performance Evidence

Evidence of the ability to:

contribute to delineating and controlling project scope

record project scope management plan

interpret and follow project initiation documentation for purposes of documenting project scope.

Note: If a specific volume or frequency is not stated, then evidence must be provided at least once.

# Knowledge Evidence

To complete the unit requirements safely and effectively, the individual must:

list components of a project scope management plan

identify and describe factors likely to impact project scope

outline formal change-control processes

identify and discuss methods for measuring work outcomes and progress against plans

identify and discuss methods for segmenting and documenting a work breakdown structure

explain procedures for reporting a change in scope

describe types of project initiation documentation.

# Assessment Conditions

Assessment must be conducted in a safe environment where evidence gathered demonstrates consistent performance of typical activities experienced in the management and leadership – project management field of work and include access to:

project documentation which includes information about project scope

case studies and, where possible, real situations.

Assessors must satisfy NVR/AQTF assessor requirements.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10