# BSBPMG421 Apply project time management techniques

Release: 1

BSBPMG421 Apply project time management techniques

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Application

This unit describes the skills and knowledge required to assist with project scheduling activities, apply and monitor the agreed project schedule, and evaluate the effectiveness of time management for the project.

The unit applies to individuals who are project practitioners working in a project support role.

No licensing, legislative, regulatory or certification requirements apply to this unit at the time of publication.

# Unit Sector

Business Competence – Project Management

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Assist in developing project schedule | 1.1 Contribute to developing work breakdown structure 1.2 Contribute to estimating duration and effort, sequence and dependencies of tasks to achieve project deliverables 1.3 Contribute to identifying schedule impact on project time management, resource requirements, costs and risks using project scheduling tools and techniques 1.4 Contribute to achieving an agreed schedule baseline and communicating the schedule to stakeholders |
| 2. Maintain project schedule | 2.1 Record and report progress of activities in relation to agreed schedule using selected tool 2.2 Record baseline variance between actual and planned progress 2.3 Contribute to forecasting impact of change on the schedule and analysing options 2.4 Update task status and agreed changes to maintain currency and accuracy of schedule |
| 3. Participate in assessing time-management outcomes | 3.1 Participate in determining effectiveness of time management from review of project performance 3.2 Contribute to document scheduling and time-management issues and responses to assist in project evaluation |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the performance criteria that are required for competent performance.

| SKILL | DESCRIPTION |
| --- | --- |
| Reading | Interprets project documentation to determine scheduling requirements and review performance |
| Writing | Documents project activities using structure, layout, vocabulary, and conventions appropriate to context |
| Oral Communication | Interacts effectively in verbal exchanges, using clear language and appropriate features to convey information Uses active listening and questioning to elicit and assess relevant information |
| Numeracy | Selects and applies a range of mathematical strategies to contribute to determining resources and measuring work output against a predetermined timeline |
| Planning and organising | Contributes to plans and implements tasks required to monitor implementation of plans Contributes to reviews and reflections on outcomes to identify whether objectives were met Uses digital tools to enter, analyse and present data and information |

# Unit Mapping Information

Supersedes and is equivalent to BSBPMG410 Apply project time management techniques.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10

Assessment Requirements for BSBPMG421 Apply project time management techniques

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with BSB Business Services Training Package Version 7.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

support project managers and other team members to apply project time management techniques during at least two different projects.

In the course of the above, the candidate must:

create a project schedule showing tasks, deliverable milestones, sequence, dependencies and time estimates

apply time-management techniques in a project

use relevant tools and techniques to maintain, monitor and update a project schedule.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

contents of work breakdown structure detail to enable effective project planning and control

implications of time management for project resources, costs and risks

methods for estimating task duration and resource requirements

tools and techniques for managing project time and their particular applications

methods to evaluate the effectiveness of time management

techniques used to measure, record and report progress of activities.

# Assessment Conditions

Skills in this unit must be demonstrated in a workplace or simulated environment where the conditions are typical of those in a working environment in this industry.

This includes access to:

workplace documentation relevant to project management

planning tools.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=11ef6853-ceed-4ba7-9d87-4da407e23c10