# CHCCDE023 Develop and deliver community projects

Release: 1

CHCCDE023 Develop and deliver community projects

# Modification History

Not applicable.

# Application

This unit describes the performance outcomes, skills and knowledge required to work with the community to develop and deliver community projects on relevant issues.

This unit applies to workers using a community development approach to carry out work in the health, community services or other sectors. Workers at this level are part of a professional team and under the guidance of a supervisor.

The skills in this unit must be applied in accordance with Commonwealth and State or Territory legislation, Australian standards and industry codes of practice.

No occupational licensing, certification or specific legislative requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Competency Field

Community Development

# Unit Sector

Community Services

# Elements and Performance Criteria

| ELEMENTS | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Develop a community project plan. | 1.1. Develop project plan to address issues of concern for target groups through participation of key stakeholders and organisations, identifying priorities and desired outcomes. 1.2. Identify and secure human, financial and physical resources for implementation of plan. 1.3. Develop strategies and educational resources and materials applicable to the context, issue and audience. 1.4. Prepare promotional materials in line with organisational policies and procedures. |
| 2. Deliver the community project. | 2.1. Implement strategies and distribute educational and promotional resources and materials to ensure maximum effectiveness for delivery of the project. 2.2. Implement strategies to encourage participation in the project and the expression of views regarding its process and content. 2.3. Make project adjustments as required to meet the needs of specific groups. 2.4. Seek feedback on the community project from participants according to organisational policies and procedures. |
| 3. Review the community project. | 3.1. Evaluate the community project against the planned goals and objectives in accordance with organisational policies and procedures. 3.2. Discuss outcomes of project evaluations with key stakeholders and organisations to determine future directions. 3.3. Document community project outcomes and act on them according to organisational policies and procedures. |

# Foundation Skills

Foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Unit Mapping Information

Supersedes and is equivalent to CHCCDE007 Develop and provide community projects.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5e0c25cc-3d9d-4b43-80d3-bd22cc4f1e53

Assessment Requirements for CHCCDE023 Develop and deliver community projects

# Modification History

Not applicable.

# Performance Evidence

Evidence of the ability to complete tasks outlined in elements and performance criteria of this unit in the context of the job role, and:

plan, deliver and evaluate at least one community project, including identifying and matching resources with activities to address community needs and priorities.

# Knowledge Evidence

Demonstrated knowledge required to complete the tasks outlined in elements and performance criteria of this unit:

Commonwealth, State or Territory legislation and public policies impacting on community development processes

social, community and youth issues impacting the local community

principles and practices of community development work:

structural disadvantage and inequality

social justice and human rights

individual

family

community

society

principles of designing and developing a community program:

community priorities assessment and analysis

asset mapping

goals and objectives for project

resource availability

strategies and actions needed to achieve goals

accountability requirements

resources and support within the community

review and evaluation

decision-making structures and processes at organisation, community, regional and system level

organisational policies and procedures for:

preparation of promotional material and dealing with the media

project evaluation

seeking feedback from stakeholders

documentation.

# Assessment Conditions

Skills must be demonstrated in the workplace or in a simulated environment that reflects workplace conditions.

Assessment must ensure:

access to facilities, equipment and resources that reflect real working conditions and model industry operating conditions and contingencies

access to Commonwealth, State or Territory legislation and public policies impacting on community development processes

access to organisational policies and procedures

opportunities for engagement with community stakeholders.

Assessors must satisfy the Standards for Registered Training Organisations’ requirements for assessors.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5e0c25cc-3d9d-4b43-80d3-bd22cc4f1e53