# CPCCBC6002 Generate and direct the development of new projects

Release: 2

CPCCBC6002 Generate and direct the development of new projects

# Modification History

| Release 2 | Updated reference to general construction induction training program. |
| --- | --- |
| Release 1 | This version first released with CPC Construction, Plumbing and Services Training Package Release 5.0. Supersedes and is equivalent to CPCCBC6002A Generate and direct the development of new projects. Updated to meet the Standards for Training Packages 2012. |

# Application

This unit of competency specifies the skills and knowledge required to generate and direct the development of new projects in a building and construction organisation involved in either residential or commercial projects.

This unit of competency applies to builders, project managers and related construction industry professionals who collate, analyse and synthesise detailed information from a range of sources to create, supervise and control the development of new projects.

Completion of the general construction induction training program specified by the model Code of Practice for Construction Work is required for any person who is to carry out construction work. Achievement of CPCWHS1001 Prepare to work safely in the construction industry meets this requirement.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil.

# Unit Sector

Building and Construction

# Elements and Performance Criteria

| Elements describe the essential outcomes. |  | Performance criteria describe what needs to be done to demonstrate achievement of the element. |  |
| --- | --- | --- | --- |
| 1 | Identify potential new projects. | 1.1 | Examine the organisation’s project history to identify projects with successful or above average outcomes for characteristic evaluation. |
|  |  | 1.2 | Review the property and construction market for available sites and buildings with development potential. |
|  |  | 1.3 | Monitor new trends in development and construction. |
|  |  | 1.4 | Analyse available statistical data on possible areas of project development. |
|  |  | 1.5 | Use network contacts to source businesses requiring new or upgraded facilities. |
|  |  | 1.6 | Short-list most promising projects and prepare preliminary costings and returns. |
| 2 | Formulate development proposals and feasibility studies. | 2.1 | Review short-listed projects to facilitate selection of preferred options for detailed design work. |
|  |  | 2.2 | Develop project briefs. |
|  |  | 2.3 | Review the environmental impact of projects and assess any existing environmental impact statements. |
|  |  | 2.4 | Carry out feasibility studies on the project’s commercial viability and ascertain the capacity to generate income through the various alternatives. |
|  |  | 2.5 | Generate accurate costings for each proposal. |
|  |  | 2.6 | Hold discussions with potential clients and investors and explain the benefits and risks of each project. |
|  |  | 2.7 | Decide to proceed once client and investor agreement is obtained. |
| 3 | Negotiate project approvals. | 3.1 | Submit project plans to relevant authorities to seek their reaction and identify any impediments to project approval. |
|  |  | 3.2 | Revise project plan to comply with authorities’ directives. |
|  |  | 3.3 | Resubmit plans for formal planning approval as necessary. |
| 4 | Obtain project finance. | 4.1 | Approach finance institutions or investors for financial support. |
|  |  | 4.2 | Obtain suitable finance package for the project from institutions or investors. |
|  |  | 4.3 | Identify and approach possible joint partners for the project and determine interest. |
| 5 | Manage the commissioning of a project. | 5.1 | Appoint and retain project consultants. |
|  |  | 5.2 | Prepare documentation for proposed project, check against the brief and send for formal building approval. |
|  |  | 5.3 | Complete detailed costing of approved documentation. |
|  |  | 5.4 | Make modifications to the project to bring it within or under budget if required. |
|  |  | 5.5 | Make final decision to proceed with the project or defer to a future date. |

# Foundation Skills

As well as the foundation skills explicit in the performance criteria of this unit, candidates require:

writing skills to:

prepare project briefs, plans and associated documentation for stakeholder /investor review, financial support and building approvals

analytical skills to:

interpret statistical data and apply calculations

interpret strategic and often ambiguous information to develop logical, supportable and practical decisions

planning and organising skills to:

sequence and schedule complex activities

utilise existing structures and systems to coordinate activities or design new processes as required

technology skills to:

use digital tools and devices to communicate and collaborate effectively with others

use equipment and programs to access, extract information and develop relevant documentation.

# Unit Mapping Information

Supersedes and is equivalent to CPCCBC6002A Generate and direct the development of new projects.

# Links

Companion volumes to this training package are available at the VETNet website - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=7e15fa6a-68b8-4097-b099-030a5569b1ad