# Assessment Requirements for CPCCDO3012 Perform crane scheduling

Release: 2

Assessment Requirements for CPCCDO3012 Perform crane scheduling

# Modification History

| Release 2 | Updated reference to general construction induction training program. |
| --- | --- |
| Release 1 | This version first released with CPC Construction, Plumbing and Services Training Package Release 5.0. Supersedes and is equivalent to CPCCDO3012A Perform crane scheduling. Updated to meet the Standards for Training Packages 2012. |

# Performance Evidence

To demonstrate competency in this unit, a candidate must meet the elements and performance criteria by scheduling the correct sequence of lifts for a minimum of three crane lifts.

# Knowledge Evidence

To be competent in this unit, a candidate must demonstrate knowledge of:

workplace and regulatory requirements for performing crane scheduling under applicable Commonwealth, state or territory work health and safety (WHS) legislation, Australian Standards and codes of practice:

job safety and environmental analyses (JSEAs)

safe work method statements (SWMSs)

safety manuals and instructions for plant, tools and equipment

signage and barricades

personal protective equipment (PPE)

environmental and worksite safety plans

reporting problems

techniques for performing crane task sequencing scheduling:

assessing lifting tasks for time required for completion

determining most efficient order for lifting tasks to coordinate with other site activities and to use resources efficiently

documenting schedules

modifying schedules

communicating schedules and changes to schedules to relevant persons

implementing work completion procedures.

# Assessment Conditions

Assessors must meet the requirements for assessors outlined in the Standards for Registered Training Organisations.

Assessment must be conducted in the workplace or a simulated workplace using realistic conditions, materials, activities, responsibilities, procedures, safety requirements and environmental considerations.

Candidates must have access to:

industry-standard equipment required to perform the tasks specified in the Performance Evidence

appropriate workplace information and records, including policies, procedures and legislative requirements.

# Links

Companion volumes to this training package are available at the VETNet website - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=7e15fa6a-68b8-4097-b099-030a5569b1ad