# Assessment Requirements for CPCMCM8001 Plan and manage complex projects

Release: 1

Assessment Requirements for CPCMCM8001 Plan and manage complex projects

# Modification History

Release 1.

This version first released with CPC Construction, Plumbing and Services Training Package Version 1.

Replaces superseded equivalent CPCMCM7001A Plan and manage complex projects.

# Performance Evidence

A person demonstrating competency in this unit must satisfy all of the elements, performance criteria and foundation skills of this unit. The person must successfully design, implement, manage and finalise two complex projects.

For each project, the person must produce a detailed project plan outlining a process and methodology for the planning, scheduling and sourcing of human and other resources. Each plan must also:

specify how the project team members will be resourced, assembled and briefed on roles, responsibilities and deliverables

outline processes for managing and communicating with a team of diverse skills and roles, including:

architects

lead contractors

mechanical engineers

hydraulic engineers

electrical engineers

specify a process for project reporting that details frequency and format of reports

ensure the project aligns to and supports organisational strategies and requirements.

For each project, the person must identify:

at least one key learning outcome from the project

where this learning could refine and improve future complex project management processes.

# Knowledge Evidence

A person demonstrating competency in this unit must be able to demonstrate knowledge of:

processes and practices involved in developing budgets

principles of team leadership and human resource management relating to managing others working on a complex project

processes involved in risk management, risk analysis and planning

legislation, codes and standards relevant to the specific project:

Australian standards

building Acts and regulations

infrastructure supply regulations

international standards

the National Construction Code

reporting mechanisms relevant to updating and informing clients and other stakeholders of project progress

roles and responsibilities of relevant building project personnel

sustainability requirements relevant to the project:

energy conservation

water conservation

tools and models of project management used in managing complex construction projects.

# Assessment Conditions

Assessment must be conducted in the workplace or a close simulation of the workplace.

Suitable assessment of performance would require:

equipment:

computer with internet and email access

proprietary software with spreadsheet and word processing functionality and project management capabilities

materials:

current legislation, codes and standards relevant to the specific project and the jurisdiction in which the project work is taking place, including:

building Acts and regulations

infrastructure supply regulations

Australian standards

international standards

project documentation, including design or project briefs, drawings, specifications, construction schedules and other supporting documents

research resources, including product information and data.

### Assessor requirements

Assessors must satisfy the assessor requirements in the Standards for Registered Training Organisations (RTOs) current at the time of assessment.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=7e15fa6a-68b8-4097-b099-030a5569b1ad