# CUAEVP511 Coordinate installation and dismantling of exhibitions

Release: 1

CUAEVP511 Coordinate installation and dismantling of exhibitions

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package Version 5.0. |

# Application

This unit describes the skills and knowledge required to organise and monitor the installation and dismantling of physical exhibition elements. It involves identifying resources required for exhibitions, planning the installation and dismantling operation and coordinating operations to complete the exhibition according to organisational policies and procedures.

The unit applies to those who work as exhibition venue staff or independent exhibition contractors in many different contexts in both business and community environments. They tend to be autonomous and may be required to lead and manage a team and consult with various exhibition stakeholders.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Cultural services – Exhibitions and visitor programs

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Identify resource requirements | 1.1 Review exhibition documentation and determine scope and type of exhibition elements required 1.2 Confirm budget and resources required for exhibition 1.3 Provide applicable input into overall planning of exhibition 1.4 Check inventory and determine additional resources required 1.5 Order additional resources as required and according to organisational policies, procedures and budgetary guidelines 1.6 Assess the need for specialist or external assistance and where required organise according to organisational policies and procedures |
| 2. Plan the installation and dismantling of exhibitions | 2.1 Determine sequence for installing and dismantling exhibitions that meets exhibition requirements in consultation with required personnel 2.2 Document plans for installation or dismantling according to organisational policies and procedures 2.3 Confirm availability of resources in advance of installation and dismantling 2.4 Organise physical resources according to organisational policies and procedures |
| 3. Coordinate exhibition installation and dismantling operations | 3.1 Provide clear instructions to required personnel relating to installing and dismantling exhibition and confirm safety and avoidance of damage to physical elements 3.2 Monitor exhibition installation and dismantling operations and confirm work is carried out according to instructions and within required budget and timeframes 3.3 Deal with problems that arise according to organisational policies and procedures 3.4 Organise storage and security of exhibition elements including valuable items and hazardous materials according to organisational policies and procedures |
| 4. Complete exhibition installation and dismantling operations | 4.1 Complete required exhibition documentation and reports and forward to required personnel as required 4.2 Seek feedback from stakeholders and team members on ways to improve exhibition installation and dismantling 4.3 Identify aspects of installation and dismantling operations that worked well and ways to enhance those aspects in future projects |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| SKILL | DESCRIPTION |
| --- | --- |
| Numeracy | Uses mathematical skills to monitor project costs, budgets and timeframes |
| Oral communication | Interacts effectively in verbal exchanges, using language and features applicable to audience and context Clarifies information and elicits the views and opinions of others using active listening and questioning techniques |
| Reading | Gathers and interprets information in different procedures, drawings, work plans and exhibition documentation |
| Writing | Develops textual information for a specific audience using clear and detailed language and numerical data and conveys information, requirements and recommendations |
| Planning and organising | Plans and schedules complex activities for self and others Takes responsibility for determining job priorities, resources and equipment Monitors progress of plans and adjust as required |
| Problem-solving | Identifies and addresses issues that arise using problem-solving skills |
| Self-management | Complies with organisational policies, procedures and regulatory requirements |
| Teamwork | Collaborates with others and plays an active role in leading work operations |

# Unit Mapping Information

Supersedes and is equivalent to CUAEVP501 Coordinate the installation and dismantling of exhibitions.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5

Assessment Requirements for CUAEVP511 Coordinate installation and dismantling of exhibitions

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package Version 5.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

coordinate the installation and dismantling of exhibitions on at least one occasion according to exhibition requirements.

In the course of the above, the candidate must:

determine exhibition elements, budget and resource requirements using required documentation

discuss and document plans for installing and dismantling exhibitions

instruct and supervise personnel who are installing and dismantling exhibition components and ensuring safe handling of all elements

manage resources, storage and security of exhibition elements

deal with disruptive issues that may arise in the context of installing and dismantling exhibitions

complete required documentation and reports.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

organisational policies, procedures and guidelines for exhibition installation and dismantling elements, including those relating to:

budget

inventory systems and procedures used for equipment and materials in the context of exhibitions

security

recordkeeping

handling physical elements, including artworks and historical objects

cultural sensitivities

disruption minimisation strategies

cleaning and waste disposal

cultural protocols that could impact on installation and dismantling

packing materials and techniques used for different types of exhibition elements

types of tools commonly used for installing and dismantling exhibitions and safe operating procedures

required organisational and legislative work health and safety (WHS) requirements, including those that affect allocation of work and movement of physical elements

roles and responsibilities of personnel involved in staging exhibitions

strategies to supervise personnel

sources of exhibition equipment and supplies

sources of specialist assistance relevant to coordinating installation and dismantling of exhibitions.

# Assessment Conditions

Skills in this unit must be demonstrated in a workplace or simulated environment where the conditions are typical of those in a working environment in this industry.

This includes access to:

exhibition venue

physical exhibition elements

exhibition documentation

organisational procedures relevant to coordinating installation and dismantling of exhibitions.

interaction with others required to demonstrate the performance evidence.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational educational and training legislation, frameworks and/or standards.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5