# CUAPPM431 Compile production schedules

Release: 1

CUAPPM431 Compile production schedules

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package Version 5.0. |

# Application

This unit describes the skills and knowledge required to compile production schedules during the pre-production planning phase in the screen, media and entertainment industry sectors. It involves analysing timelines against overall production requirements to deliver productions on time and on budget.

The unit applies to those who work collaboratively in a production team as senior production personnel. Depending on the size of the production, this person may also be responsible for developing the resource schedule on which the production schedule is based.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Media and Live Entertainment Production – Production Planning and Management

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Confirm resources required | 1.1 Analyse resource schedule to identify internal and external resources required 1.2 Consult with all departments involved in the production to clarify and confirm their requirements 1.3 Confirm resource schedule against overall production requirements 1.4 Identify and document issues that may affect production schedule |
| 2. Compile production schedules | 2.1 Allocate resources and create schedule that will deliver production on time and within budget 2.2 Check allocated time enables efficient and safe use of resources 2.3 Identify factors that may cause production delays and develop contingency plans to accommodate them |
| 3. Finalise production schedules | 3.1 Confirm production schedule meets production requirements 3.2 Distribute schedule promptly to required personnel 3.3 Resolve issues with the interpretation or implementation of schedule as required 3.4 Revise schedule as required, and communicate changes promptly 3.5 Develop and maintain a recording system for all information relating to production schedule |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| SKILL | DESCRIPTION |
| --- | --- |
| Reading | Interprets textual information to determine requirements Interprets information in a variety of forms and uses the knowledge gained to evaluate and select required schedule content Checks scheduling information for feasibility and consistency with production requirements |
| Writing | Uses clear and detailed language, and industry terminology to complete and update comprehensive workplace documentation |
| Oral Communication | Uses clear language to contribute information and express requirements Uses listening and questioning techniques to confirm understanding |
| Numeracy | Calculates with whole numbers and routine fractions, decimals or percentages to develop production schedules that reflect allocated budgets and required timeframes |
| Self-management | Understands purpose of own role and associated responsibilities to deliver schedules that meet production budget and timelines |
| Teamwork | Selects and uses effective communication techniques to build rapport to establish and maintain effective working relationships |
| Planning and organising | Plans and organises own workload logically and systematically to complete clearly defined tasks and manage required communication Uses information analysis to inform detailed scheduling decisions Builds flexibility into schedules to manage adjustments and unexpected events |
| Technology | Identifies and resolves user implementation problems Uses scheduling software efficiently Develops effective information management systems for production schedules |

# Unit Mapping Information

Supersedes and is equivalent to CUAPPM411 Compile production schedules.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5