# CUAPPM611 Manage pre-production for shows and events

Release: 1

CUAPPM611 Manage pre-production for shows and events

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package Version 5.0. |

# Application

This unit describes the skills and knowledge required to manage all aspects of pre-production for shows and events in the entertainment industry, including both creative and technical aspects of live shows and events.

The unit applies to those who exercise autonomy and judgement in contexts that are subject to change and are responsible for coordinating and supervising the work of team members engaged in a wide range of pre-production activities.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Media and Live Entertainment Production – Production Management

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Plan pre-production activities | 1.1 Participate in discussions with required personnel to clarify creative vision for shows or events 1.2 Analyse designs and specifications to establish a comprehensive understanding of production requirements and challenges 1.3 Determine the range and number of staging and technical elements required for shows 1.4 Develop work plans and schedules to ensure timely completion of each stage of pre-production 1.5 Conduct risk assessments and implement safety and environmental management plans during pre-production as required 1.6 Develop contingency plans to minimise the impact of unexpected events on pre-production operations 1.7 Provide advice to required personnel regarding technical, artistic and safety issues that may affect shows or events |
| 2. Coordinate production meetings | 2.1 Allocate times for production meetings 2.2 Chair production meetings to discuss and resolve artistic and technical issues 2.3 Prepare and distribute clear and timely reports on the progress of pre-production activities 2.4 Notify colleagues of meeting outcomes and budget issues that affect their work activities 2.5 Keep accurate records of decisions made and actions required |
| 3. Monitor and undertake pre-production activities | 3.1 Take an active role in maintaining a creative and technical overview of projects and take action to resolve problems that arise 3.2 Liaise with technical and artistic production teams 3.3 Monitor the progress of pre-production activities against timelines and budget, and implement contingency plans as required 3.4 Determine the need for additional resources and take action accordingly 3.5 Contribute to evaluations of shows or events and implement recommendations |
| 4. Manage production documentation and information | 4.1 Confirm that production documentation is completed on time by required personnel 4.2 Distribute production documentation and information to required personnel according to organisational procedures 4.3 Develop and maintain accurate document distribution records 4.4 Review and update documentation to reflect changes to production requirements 4.5 Manage production budget and follow organisational financial procedures in relation to purchases and record keeping |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| SKILL | DESCRIPTION |
| --- | --- |
| Reading | Obtains information from a range of complex written sources |
| Writing | Generates and updates documentation in relation to pre-production activities in the required format |
| Oral communication | Seeks the views and opinions of others and obtains information by listening and questioning Discusses ideas and solutions and uses clear language to contribute information and express requirements |
| Numeracy | Interprets budgets when managing pre-production for shows and events |
| Self-management | Works independently and collectively with a strong sense of responsibility for goals, plans, decisions and outcomes Takes responsibility for meeting legal and regulatory requirements within scope of own role Applies organisational procedures when managing live productions Manages time efficiently to meet work deadlines |
| Teamwork | Collaborates with team members and takes a leadership role to help facilitate effective group interaction and direction |
| Planning and organising | Sequences and schedules complex activities, monitors implementation and manages required communication Assembles documentation on pre-production requirements in a logical sequence Reviews progress against goals, adjusting plans and resources to cope with contingencies Takes account of a wide range of factors that impact on pre-production activities Proactively anticipates potential resolutions to problems that could disrupt construction workshop operation Implements improvements to pre-production operations based on outcome of evaluations |
| Technology | Distributes information electronically Uses standard word processing and spreadsheet applications to prepare workplace documentation Applies knowledge of technical equipment to production management duties |

# Unit Mapping Information

Supersedes and is equivalent to CUAPPM601 Manage pre-production for shows and events.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5

Assessment Requirements for CUAPPM611 Manage pre-production for shows and events

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package Version 5.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

manage pre-production operations for at least one production or event.

In the course of the above, the candidate must:

document work plans and schedules for pre-production activities that include timelines

monitor activities against the plans and schedules

coordinate and chair at least one production meeting

manage the distribution and maintenance of documents during pre-production operations.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

relationship between artistic and technical elements of productions or events

meeting procedures and protocols that apply to conducting production meetings

issues and challenges that typically arise during pre-production, and strategies for responding to them

administrative procedures and documentation associated with managing pre-production activities

safety and environmental requirements during the pre-production phase of shows and events.

# Assessment Conditions

Skills in this unit must be demonstrated in a live production environment where the conditions are typical of those in a working environment in this industry.

This includes access to a production or event which requires a range of pre-production activities.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational education and training legislation, frameworks and/or standards. Where personal safety is a limiting factor, assessment may occur in a simulated work environment typical of those in a working environment in this industry.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5