# CUAPPM614 Plan and manage post-production activities

Release: 1

CUAPPM614 Plan and manage post-production activities

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package version 5.0. |

# Application

This unit describes the skills and knowledge required to plan and manage post-production processes and facilities. It involves supervising personnel and acquiring post-production resources.

The unit applies to those who are responsible for implementing the post-production process on time and within budget. They may work as post-production supervisors in the film and media industry or other industry, often managing a number of projects simultaneously.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Media and entertainment production – Production planning and management

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Clarify post-production briefs | 1.1 Confirm and analyse technical and creative requirements for post-production 1.2 Participate in meetings with production personnel and determine required post-production resources according to selected production medium 1.3 Provide advice on cost and operational implications for editing, taking into account techniques used for production 1.4 Confirm budget and timeline with required personnel |
| 2. Develop operational plans | 2.1 Draw up schedule for post-production activities according to agreed timelines 2.2 Investigate and confirm availability and cost of post-production resources and staff 2.3 Document post-production stages and confirm with required production personnel 2.4 Confirm work health and safety (WHS) requirements are established in line with organisational procedures 2.5 Finalise operational plan in consultation with production personnel, and obtain sign-off according to organisational procedures |
| 3. Implement post-production processes | 3.1 Book and check post-production resources and finalise contractual arrangements as required in line with organisational procedures 3.2 Confirm documentation is accessible to required personnel involved with post-production activities 3.3 Identify any problems and discuss proposed solutions with required personnel 3.4 Negotiate provision of unplanned and additional post-production services with required production personnel 3.5 Monitor and manage post-production activities and staff proactively and according to agreed operational plan 3.6 Prepare progress reports according to organisational procedures and organise review sessions with required production personnel |
| 4. Wrap up post-production processes | 4.1 Attend post-production evaluation session and confirm final product meets creative, technical and budgetary requirements of production 4.2 Obtain lock-off approval for project from required production personnel 4.3 Complete required documentation and arrange for return of hired post-production resources 4.4 Evaluate all aspects of completed projects and note areas for future improvement |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| SKILL | DESCRIPTION |
| --- | --- |
| Numeracy | Interprets and adjusts numerical information for budgets and service costs Calculates periods of time when allocating resources |
| Oral communication | Articulates requirements and strategies using language required for audience and environment Uses listening and questioning techniques in discussion of complex ideas, opinions and concepts with a wide range of people |
| Reading | Analyses complex documentation and determines requirements |
| Writing | Creates documentation which demonstrate comprehension of outcomes and alternatives Uses concise vocabulary, syntax and grammar |
| Planning and organising | Monitors work progress and determines actions required in line with operational plan and schedule requirements Plans and sequences complex tasks and workload, and manages required communication |
| Problem solving | Develops solutions to production process problems |
| Self-management | Selects and uses accepted communication methods and practices for sharing information and determining requirements Works independently and collectively in making decisions in line with achieving requirements Takes responsibility for following procedures, organisational policies and workplace safety legislation Identifies improvement opportunities from evaluation processes |
| Teamwork | Facilitates agreement and achieves joint outcomes by collaborating, consulting and negotiating with post-production team and other service providers |

# Unit Mapping Information

Supersedes and is equivalent to CUAPPM604 Plan and manage film and media post-production.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5

Assessment Requirements for CUAPPM614 Plan and manage post-production activities

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package version 5.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

plan and manage post-production according to requirements of at least two different productions.

In the course of the above, the candidate must:

clarify post-production briefs and creative and technical requirements of post-production

coordinate all post-production activities and meetings and brief personnel

produce creative solutions

respond to different issues and problems encountered during post-production in line with established protocols and procedures

generate and distribute production documentation and reports relating to post-production process.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

structure of a post-production process, roles and responsibilities of those involved, and their relationship to the post-production supervisor

production requirements that affect planning and managing post-production including:

length of shoot

budget constraints

standards of issue resolution

technical and creative feasibility

resource and personnel requirements

timelines

organisational procedures as they relate to developing operational plans and implementing post-production processes

administrative procedures associated with a post-production operation

phases and practices in the post-production process, including editing and post-production services, and outline typical issues that may arise and their possible solutions

work health and safety (WHS) requirements that apply to post-production environments.

# Assessment Conditions

Skills in this unit must be demonstrated in a workplace or simulated environment where the conditions are typical of those in a working environment in this industry.

This includes access to:

post-production activities across different formats

post-production resources and equipment

interaction with others required to demonstrate the performance evidence

standard employment contracts and supplier agreements.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational educational and training legislation, frameworks and/or standards.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5