# CUASMT403 Develop and implement production work plans

Release: 2

CUASMT403 Develop and implement production work plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 2 | This version released with CUA Creative Arts and Culture Training Package version 2.0. Updated assessment conditions section. Updated modification history section to reflect changed name of training package. |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package version 1.0. |

# Application

This unit describes the performance outcomes, skills and knowledge required to analyse production information to identify technical and creative elements that need to be addressed in work plans for productions in the screen, media, entertainment and events industries.

Individuals who apply these skills work autonomously in a team environment as they take responsibility for documenting and implementing work plans that contribute to the achievement of the overall creative vision for shows or events. They may be responsible for supervising others.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

Media and entertainment production - stage management

# Elements and Performance Criteria

| Elements Elements describe the essential outcomes. | Performance Criteria Performance criteria describe the performance needed to demonstrate achievement of the element. |
| --- | --- |
| 1.Analyse production information | 1.1 Obtain production information from relevant colleagues 1.2 Analyse production information to determine overall creative and technical parameters for productions 1.3 Discuss own analysis with colleagues to confirm preliminary interpretation is consistent with overall creative vision 1.4 Undertake research to assist with providing context for productions as required 1.5 Extend creative and technical ideas that could contribute to the realisation of creative vision |
| 2. Document production requirements | 2.1 Produce a detailed breakdown of creative, production and technical requirements applicable to own area of responsibility 2.2 Identify requirements that need collaboration with colleagues 2.3 In consultation with colleagues, develop concepts and strategies that address joint issues and provide creative input into productions |
| 3. Implement work plans | 3.1 Incorporate information gained from analysis and consultation into relevant documentation and planning processes 3.2 Integrate key information into work plans within agreed timeframes 3.3 Identify factors that could affect the achievement of work objectives and establish contingencies and incorporate them into work plans 3.4 Implement work plans and monitor progress to ensure work achieves objectives, meets deadlines and remains consistent with overall creative vision |
| 4. Review work plans | 4.1 Contribute to evaluations aimed at improving production services and adjust own work procedures accordingly 4.2 Negotiate and agree on modifications to work plans and amend accordingly 4.3 Agree to final designs and produce accurate and comprehensive documentation to support implementation in line with production schedules 4.4 Present final designs, plans and specifications within agreed timeframes and confirm that production requirements have been met |

# Foundation Skills

This section describes language, literacy, numeracy and employment skills incorporated in the performance criteria that are required for competent performance.

| Skill | Performance Criteria | Description |
| --- | --- | --- |
| Learning | 4.1 | Interprets information from evaluation to enhance own performance |
| Reading | 1.2, 1.4, 2.1, 3.4 | Obtains information from a range of complex written sources |
| Writing | 2.2, 3.2 | Develops workplace documents and plans |
| Oral communication | 1.1, 1.3, 1.5, 2.2, 2.3, 3.3, 4.1 | Obtains information by listening and questioning Seeks the views and opinions of others Discusses ideas and solutions Uses clear language to contribute information and express requirements |
| Navigate the world of work | 2.1, 2.2, 3.4 | Takes responsibility for decisions about when and how to complete tasks and coordinate with others Applies organisational procedures and meets expectations associated with own role |
| Interact with others | 1.1, 1.3, 1.5, 2.2, 2.3, 3.3, 4.1 | Shares information and resources and offers assistance Collaborates with creative and technical personnel to achieve joint outcomes, playing an active role in facilitating effective group interaction |
| Get the work done | 1.1, 1.2, 1.3, 1.4, 1.5, 2.1, 2.2, 2.3, 3.1, 3.2, 3.3, 3.4 | Adopts a methodical and logical approach to the development of work plans Implements plans, making adjustments if necessary and addressing unexpected issues Plans and organises own workload, planning for contingencies and considering how to link with the work of others Undertakes research to enhance understanding and appreciation of production contexts Uses the internet as a research tool Uses standard word processing and spreadsheet applications to prepare production documentation |

# Unit Mapping Information

| Code and title current version | Code and title previous version | Comments | Equivalence status |
| --- | --- | --- | --- |
| CUASMT403 Develop and implement production work plans (Release 2) | CUASMT403 Develop and implement production work plans (Release 1) | Updated assessment conditions section. Updated modification history section to reflect changed name of training package. | Equivalent unit |

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5

Assessment Requirements for CUASMT403 Develop and implement production work plans

# Modification History

| Release | Comments |
| --- | --- |
| Release 2 | This version released with CUA Creative Arts and Culture Training Package version 2.0. Updated assessment conditions section. Updated modification history section to reflect changed name of training package. |
| Release 1 | This version first released with CUA Creative Arts and Culture Training Package version 1.0. |

# Performance Evidence

Evidence of the ability to:

document creative and technical requirements based on an analysis of production information in area of specialisation for at least two productions

develop and implement work plans to achieve production requirements in area of specialisation on at least two occasions

work collaboratively

meet work deadlines.

Note: If a specific volume or frequency is not stated, then evidence must be provided for each of the above points at least once.

# Knowledge Evidence

To complete the unit requirements the individual must:

explain the purpose of a range of documentation required for the planning of work operations

explain key factors involved in ensuring that work plans address production requirements in area of specialisation

describe issues and challenges that can arise when developing and implementing work plans, along with solutions to address them

describe broad historical and cultural context for productions relevant to area of specialisation.

# Assessment Conditions

Assessment must be conducted in a safe environment where evidence gathered demonstrates consistent performance of typical activities experienced in creative arts industry environments. The assessment environment must include access to productions and production information from which to develop work plans.

Assessors of this unit must satisfy the requirements for assessors in applicable vocational educational and training legislation, frameworks and/or standards.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1db201d9-4006-4430-839f-382ef6b803d5