# CULMS504C Organise and monitor exhibition installation/dismantling

Revision Number: 1

CULMS504C Organise and monitor exhibition installation/dismantling

# Modification History

Not applicable.

# Unit Descriptor

| Unit descriptor | This unit describes the performance outcomes, skills and knowledge required to plan and oversee the installation and dismantling of physical exhibition elements. No licensing, legislative, regulatory or certification requirements apply to this unit at the time of endorsement. |
| --- | --- |

# Application of the Unit

| Application of the unit | Exhibitions take place in many different contexts and environments across both businesses and the community. This unit allows for broad application and work may be undertaken by exhibition venue staff or by independent exhibition contractors. Exhibitions may be temporary or permanent in nature. The unit requires the application of planning and organisational skills in a team leadership or managerial capacity. Work is undertaken autonomously in consultation with various exhibition stakeholders. Operational level exhibition installation and dismantling skills are covered in CULMS407C Install and dismantle exhibition elements. |
| --- | --- |

# Licensing/Regulatory Information

Not applicable.

# Pre-Requisites

| Prerequisite units | Nil |
| --- | --- |

# Employability Skills Information

| Employability Skills | The required outcomes described in this unit of competency contain applicable facets of Employability Skills. The Employability Skills Summary for the qualification in which this unit of competency is packaged, will assist in identifying Employability Skills requirements. |
| --- | --- |

# Elements and Performance Criteria Pre-Content

| Elements describe the essential outcomes of a unit of competency. | Performance criteria describe the performance needed to demonstrate achievement of the element. Where bold italicised text is used, further information is detailed in the required skills and knowledge section and the range statement. Assessment of performance is to be consistent with the evidence guide. |
| --- | --- |

# Elements and Performance Criteria

| ELEMENT |  | PERFORMANCE CRITERIA |  |
| --- | --- | --- | --- |
| 1 | Identify and organise physical resource requirements | 1.1 | Correctly interpret exhibition documentation to determine the scope and type of physical elements required |
|  |  | 1.2 | Take account of universal access principles in determining resource requirements |
|  |  | 1.3 | Consult with relevant colleagues to discuss and confirm requirements and provide appropriate input to overall exhibition development |
|  |  | 1.4 | Complete accurate inventory checks to determine availability of physical resources |
|  |  | 1.5 | Identify the need for additional resources and order or undertake organisation of physical resources in accordance with organisational procedures and relevant budgetary guidelines |
|  |  | 1.6 | Identify the need for specialist or external assistance and organise in accordance with organisational procedures and relevant budgetary guidelines |
| 2 | Make plans for exhibition installation/ dismantling | 2.1 | Liaise with other exhibition personnel to determine most effective order for the installation/dismantling process |
|  |  | 2.2 | Identify and organise relevant physical resource requirements in consultation with other personnel and in accordance with organisational procedures |
|  |  | 2.3 | Make realistic estimates of the numbers of people required for installation/dismantling and provide information to relevant personnel |
|  |  | 2.4 | Clearly and accurately document plans for installation/dismantling in accordance with organisational procedures |
|  |  | 2.5 | Confirm availability of all resources in advance of installation/dismantling |
| 3 | Monitor exhibition installation/ dismantling | 3.1 | Provide clear instructions to relevant personnel in relation to installation/dismantling to ensure safety and avoid damage to physical elements |
|  |  | 3.2 | Monitor the process to ensure that work is carried out in accordance with instructions |
|  |  | 3.3 | Organise appropriate storage and security of exhibition elements, including valuable items and any hazardous materials |
| 4 | Complete exhibition reports | 4.1 | Complete relevant exhibition documentation and reports on installation/dismantling and forward to relevant personnel |
|  |  | 4.2 | Identify ways in which processes could potentially be enhanced and include relevant suggestions in reports |

# Required Skills and Knowledge

REQUIRED SKILLS AND KNOWLEDGE

This section describes the skills and knowledge required for this unit.

Required skills

communication skills to consult with various stakeholders and exhibition participants and to lead an installation team planning and organisational skills to plan, coordinate and monitor the interrelated elements of exhibition installation/dismantling literacy skills to interpret and develop operational documentation numeracy skills to interpret budgets, estimate costs and work with concepts around dimensions and location capacities.

Required knowledge

installation/dismantling process planning and organisational requirements for exhibition installation/dismantling, roles of key personnel and typical issues and problems encountered inventory systems and procedures used for equipment and materials in an exhibition's context sources of additional equipment and supplies for different exhibition elements sources of specialist assistance relevant to the work context occupational health and safety requirements that affect the allocation of work and the movement of physical elements environmental and other risk factors for people and physical elements principles of universal access and impact on installation technical procedures for handling physical elements in the relevant work context, e.g. artworks, historical objects cultural protocols that impact on installation/dismantling, including those for Aboriginal or Torres Strait Islander material.

# Evidence Guide

| EVIDENCE GUIDE |  |
| --- | --- |
| The Evidence Guide provides advice on assessment and must be read in conjunction with the performance criteria, required skills and knowledge, range statement and the Assessment Guidelines for the Training Package. |  |
| Critical aspects for assessment and evidence required to demonstrate competency in this unit | Evidence of the following is essential: demonstration of skills through the coordination of installation/dismantling process detailed knowledge of the exhibition set-up process in the relevant industry context application of organisational, planning and problem-solving skills. |
| Context of and specific resources for assessment | Assessment must ensure: involvement of and interaction with a team for whom the candidate can plan and organise work access to an exhibition and exhibition venue access to physical exhibition elements access to exhibition documentation. |
| Method of assessment | A range of assessment methods should be used to assess practical skills and knowledge. The following examples are appropriate for this unit: direct questioning combined with review of portfolios of evidence and third party workplace reports of on-the-job performance by the candidate evaluation of an installation coordinated by the candidate evaluation of reports prepared by the candidate detailing methods used to organise installation/dismantling, challenges faced and how these were resolved evaluation of candidate responses to case studies and problem-solving exercises to assess ability to plan for different situations and contexts. |
|  | Holistic assessment with other units relevant to the industry sector, workplace and job role is recommended, for example: BSBFLM412A Promote team effectiveness. |

# Range Statement

| RANGE STATEMENT |  |
| --- | --- |
| The range statement relates to the unit of competency as a whole. It allows for different work environments and situations that may affect performance. Bold italicised wording, if used in the performance criteria, is detailed below. Essential operating conditions that may be present with training and assessment (depending on the work situation, needs of the candidate, accessibility of the item, and local industry and regional contexts) may also be included. |  |
| An exhibition may be held in many different contexts /environments, and these may include: | museums galleries libraries other visitor attractions theme parks corporate events festivals |
| An exhibition may be: | temporary permanent travelling developed in-house or externally hired, borrowed or presented on behalf of another organisation or community group |
| Exhibition documentation may include: | site plans floor plans event orders concept documentation |
| Appropriate input to overall exhibition development may relate to: | operational feasibility of ideas own ideas for enhancement of concept or design safety issues |
| Additional resources may include: | lighting audio vision systems display or other furniture costumes scenic items |
| Organisation of physical resources may relate to: | preparation of the site transportation packing, moving and handling of objects or other display items security safety waste management storage disposal recruitment/rostering of additional staff |
| Specialist or external assistance may include: | designers artists preparators printers conservators builders electricians other trades people |

# Unit Sector(s)

Not applicable.

# Competency field

| Competency field | Exhibition Development and Management |
| --- | --- |