# ICTICT520 Confirm transition strategy for new systems

Release: 1

ICTICT520 Confirm transition strategy for new systems

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with ICT Information and Communications Technology Training Package Version 6.0. |

# Application

This unit describes the skills and knowledge required to confirm a transition strategy for new systems based on a revised system design and newly developed change management plan.

The unit applies to those who work as part of a team in a range of information and communications technology (ICT) positions and who are required to plan for a transition to new system websites, networks or software.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Unit Sector

General ICT

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Confirm delivery and acceptance plan | 1.1 Evaluate revised system design and change management plan 1.2 Confirm phased delivery with client and project team 1.3 Confirm method of acceptance and acceptance criteria 1.4 Confirm that acceptance test plan is in place and agreed |
| 2. Develop and confirm data take-up plan | 2.1 Identify data source for each database 2.2 Analyse potential integrity constraints 2.3 Design data conversion workflow 2.4 Identify interface requirements, data take-up method, complexity and effort required 2.5 Develop required data conversion contingencies and confirm with required personnel |
| 3. Confirm cutover plan | 3.1 Agree on conversion window in operational timescale with required personnel 3.2 Plan and confirm parallel running with required personnel 3.3 Determine and confirm approval of dependencies with required personnel 3.4 Determine and confirm approval of fall-back options with required personnel 3.5 Confirm approval of checkpoints, tests and responsibilities with required personnel 3.6 Confirm approval of resources, tasks and timescales with required personnel |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| SKILL | DESCRIPTION |
| --- | --- |
| Reading | Identifies and analyses complex electronic and hard copy documentation, information and data containing specific terminology, diagrams and numerical information to organise conversion and identify data convention contingencies |
| Writing | Applies formal labels, logos, formatting and document structure required by the organisation to ensure signoff obtained is valid |
| Oral Communication | Articulates strategies clearly and distinctively, based on techniques and language specific to audience and environment, and uses probing, clarifying questions to ensure strategies are understood |
| Numeracy | Interprets and analyses numerical and financial information and applies mathematical calculations and financial functions related to timeframe, logistics and budgets |
| Planning and organising | Applies formal processes when planning more complex tasks, producing plans with logically sequenced steps and reflecting some awareness of resource constraints Uses analytical processes in a variety of situations, setting goals, gathering relevant information and identifying and evaluating options against agreed criteria |
| Technology | Demonstrates a sophisticated understanding of principles, concepts, language and practices associated with the digital world and uses these to troubleshoot |

# Unit Mapping Information

Supersedes and is equivalent to ICTICT504 Confirm transition strategy for a new system.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=a53af4e4-b400-484e-b778-71c9e9d6aff2