# LGAOPS003 Develop works maintenance schedule

Release: 1

LGAOPS003 Develop works maintenance schedule

# Modification History

Not applicable.

# Application

This unit describes the performance outcomes, skills and knowledge required to develop works maintenance schedules to meet council asset management program outcomes. It requires the ability to identify works priorities according to visual inspections and customer feedback, and develop work plans to meet council budgetary and asset management requirements.

This unit applies to individuals working in local government and undertaking tasks related to the maintenance of council assets.

The skills in this unit must be applied in accordance with Commonwealth and State or Territory legislation, Australian standards and industry codes of practice.

No occupational licensing, certification or specific legislative requirements apply to this unit at the time of publication.

# Competency Field

Not applicable.

# Unit Sector

Not applicable.

# Elements and Performance Criteria

| ELEMENTS | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Prioritise works requirements. | 1.1. Interpret and analyse information from asset management system, visual inspections and customer feedback to identify works requirements. 1.2. Prioritise works requirements according to organisational policies and procedures. 1.3. Identify and record critical assets for ongoing monitoring and remedial action. |
| 2. Prepare works schedule. | 2.1. Analyse works requirements to confirm scope of works. 2.2. Prepare preliminary estimate of resources and scheduling according to scope and priorities. 2.3. Prepare a feasibility plan to complete the work according to council budget and planning estimate processes. 2.4. Review recently completed works to determine preliminary costs of design and construction. 2.5. Document works schedule according to organisational policies and procedures. |
| 3. Assess works proposals. | 3.1. Assess works proposals against council budget allocation. 3.2. Assess works proposals against the asset management program. 3.3. Prioritise proposed maintenance works according to assessment outcomes. 3.4. Allocate resources according to demand and asset management program. |
| 4. Complete documentation. | 4.1. Prepare and submit reports and recommendations according to organisational policies and procedures. 4.2. Update asset management system according to organisational policies and procedures. |

# Foundation Skills

| Foundation skills essential to performance in this unit, but not explicit in the performance criteria are listed below. |  |
| --- | --- |
| SKILLS | DESCRIPTION |
| Reading skills to: | interpret plans, maps, charts, databases, Safe Work Method Statements(SWMS) and specifications. |
| Writing skills to: | correspond with colleagues and customers. |
| Oral communication skills to: | clarify information with colleagues and customers present information and recommendations. |
| Numeracy skills to: | interpret mathematical information in plans, maps, charts, databases and specifications interpret and analyse financial information in budgets and life-cycle costings associated with works maintenance schedules sequence and schedule works activities. |
| Technology skills to: | use asset management system. |

# Unit Mapping Information

LGAWORK401A Develop works maintenance schedule.

# Links

Companion Volume Implementation Guide are available in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=0388d502-0fc3-49d9-a06e-c95893d7

Assessment Requirements for LGAOPS003 Develop works maintenance schedule

# Modification History

Not applicable.

# Performance Evidence

Evidence of the ability to complete tasks outlined in elements and performance criteria of this unit in the context of the job role, and:

develop one works maintenance schedule that involves:

adhering to council budget and planning estimate processes

using an assets register

allocating resources according to the asset management program

reporting information and recommendations

communicating with colleagues and customers.

# Knowledge Evidence

Demonstrated knowledge required to complete the tasks outlined in elements and performance criteria of this unit:

organisational policies and procedures applicable to developing works maintenance schedules

legislation applicable to developing works maintenance schedules

types and availability of works maintenance resources

council assets network

maintenance history of assets

risk assessment process

purpose and components of Safe Work Method Statements (SWMS)

research and scope of works projects

council priorities impacting on works maintenance schedules

types and components of plans, maps, databases and specifications

works maintenance schedule, budget and life-cycle costings.

# Assessment Conditions

Skills must be demonstrated in the workplace or in a simulated work environment that reflects workplace conditions in a local government environment.

Assessment must ensure access to:

organisational policies and procedures applicable to developing works maintenance schedules.

Assessment must ensure use of:

assets register

asset management system

customer requests

work plans and proposals

budget and planning estimates

colleagues and council customers.

Assessors must satisfy the Standards for Registered Training Organisations’ requirements for assessors.

# Links

Companion Volume Implementation Guide are available in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=0388d502-0fc3-49d9-a06e-c95893d7