# MEM22013 Coordinate engineering projects

Release: 1

MEM22013 Coordinate engineering projects

# Modification History

Release 1. Supersedes and is equivalent to MEM22013A Coordinate engineering projects.

# Application

This unit of competency defines the skills and knowledge required to coordinate and facilitate engineering or related projects which usually have a fixed term or purpose and involve specific engineering-related tasks, such as installation and commissioning of plant, design of equipment or major overhauls. It applies to coordination activities carried out within a range of engineering disciplines.

No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

MEM16006 Organise and communicate information

# Competency Field

Management and organisation

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Review and confirm parameters of delegated project | 1.1 Follow standard operating procedures (SOPs) 1.2 Comply with work health and safety (WHS) requirements at all times 1.3 Establish scope and parameters of the engineering project from work information 1.4 Assess procurement requirements 1.5 Determine the need for appropriate technical and professional assistance based on project parameters 1.6 Review compliance requirements for project |
| 2. Establish communication arrangements for delegated project | 2.1 Assign work based on project requirements and obtain team agreement to plans, communication arrangements, responsibilities, schedules and requirements 2.2 Establish liaison arrangements with other functional groups 2.3 Ensure efficient and documented arrangements for requests for further information (RFIs) from designers and other experts 2.4 Confirm internal and external reporting requirements including content, schedule and sign-off arrangements 2.5 Confirm suppliers, contractors and delivery schedules and any installation requirements |
| 3. Coordinate implementation of delegated project | 3.1 Coordinate actions to overcome constraints and contingencies, including coordination with stakeholders and make any required adjustments to plans and schedules 3.2 Coordinate and monitor specialist and technical support services to meet schedules, budgets and performance requirements 3.3 Maintain and monitor records of project tasks for accountability against objectives, schedule and budget 3.4 Apply principles of continuous improvement to implementation 3.5 Use project management, resources control and budgeting software |
| 4. Report on outcomes | 4.1 Record progress in accordance with procedures 4.2 Supervise project completion, including sign-off of project documentation in accordance with procedures |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance.

Foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Range of Conditions

| This field allows for different work environments and conditions that may affect performance. Essential operating conditions that may be present (depending on the work situation, needs of the candidate, accessibility of the item, and local industry and regional contexts) are included. |  |
| --- | --- |
| Project parameters include those related to: | designs drawings standards established implementation plan and schedule budget and control measures project management structure functional team relationships communications and reporting lines materials, logistics and services procurement requirements physical, human and skills development resources requirements. |
| Regulatory and compliance requirements include: | work health and safety (WHS) requirements codes of practice regulations standards legal and other regulatory requirements enterprise procedures environmental protection and planning law risk assessments registration requirements safe work practices state and territory regulatory requirements. |
| Project context includes: | customer-supplier relationships regulatory requirements and environment materials resourcing and labour and skills supply arrangements market and competitive environment. |
| Budget and control measures for engineering-related projects include one or more of the following: | audit tenders contracts schedules budget categories and items. |
| Stakeholders include one or more of the following: | teams contractors support professionals and teams technicians functional groups customers suppliers. |
| Records of project includes one or more of the following: | tenders and contracts schedules personnel resource allocations and financial management procedures standard operating procedures, including maintenance procedures WHS committee minutes and action risk management and mitigation documentation and records of current safe work method statements (SWMS), safety data sheets (SDS), work permits, standards and codes of practice audits meetings and communications graphics and specifications. |
| Continuous improvement implementation includes one or more of the following techniques: | balanced scorecard current and future state mapping measuring performance against benchmarks process improvement, problem-solving and decision-making data management, generation, recording, analysing, storing and use of software training for improvement systems participation technical training. |
| Appropriate technical and professional assistance includes: | technical support and advice relating to elements which have intrinsic dangers professional and technical support for specific technologies and equipment professional services for: finance, accounts and tax insurance and legal training and human resources. |
| Constraints and contingencies include: | financial, organisational, procedural or culture constraints physical constraints including limits to resources, site access or logistical limitations. |

# Unit Mapping Information

Release 1. Supersedes and is equivalent to MEM22013A Coordinate engineering projects.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=b7050d37-5fd0-4740-8f7d-3b7a49c10bb2