# MSFKB3012 Plan kitchen and bathroom projects

Release: 1

MSFKB3012 Plan kitchen and bathroom projects

# Modification History

Release 1. Changes to code, application, elements, performance criteria, assessment requirements. Foundation skills added. Range of conditions removed. Assessment requirements changed.

# Application

This unit describes the skills and knowledge required to plan kitchen and bathroom renovation and new-build projects, including sequencing of cabinetry installation and other work.

Workers with this competency include kitchen and bathroom designers, sales advisors and tradespeople involved in kitchen and bathroom construction at different stages of the process.

No licensing or certification requirements exist at the time of publication. Relevant legislation, industry standards and codes of practice within Australia must be applied.

# Competency Field

Kitchens and Bathrooms

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Determine project scope | 1.1 Seek information about the project through direct client communication or review of documentation 1.2 Establish scope and complexity of project from information provided 1.3 Establish key people and organisations to be involved in the project and their respective roles and responsibilities |
| 2. Assess individual work requirements | 2.1 Determine own work responsibilities from review of project information 2.2 Agree communication lines and protocols with individuals whose role intersects with, and impacts on, own responsibilities 2.3 Confirm and document detailed sequencing details with others involved in the project |
| 3. Plan work | 3.1 Develop and document a project schedule that reflects work requirements 3.2 Address the contingencies involved in project sequencing in consultation with others 3.3 Confirm and communicate work schedule to others involved in the project in a timely manner |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

Reading skills to interpret work documentation

Writing skills to communicate project sequence

Oral communication skills to liaise with others working on project

Other foundation skills essential to performance are explicit in the performance criteria of this unit.

# Unit Mapping Information

Release 1. Supersedes and is equivalent to MSFKB3011 Plan kitchen and bathroom projects.

# Links

Companion Volume implementation guides are found in VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=0601ab95-583a-4e93-b2d4-cfb27b03ed73

Assessment Requirements for MSFKB3012 Plan kitchen and bathroom projects

# Modification History

Release 1. Changes to code, application, elements, performance criteria, assessment requirements. Foundation skills added. Range of conditions removed. Assessment requirements changed.

# Performance Evidence

There must be evidence the candidate has completed the tasks outlined in the elements and performance criteria of this unit, and:

planned and documented the work process for 3 different projects, 1 of which must be a kitchen and 1 of which must be a bathroom.

# Knowledge Evidence

There must be evidence the candidate has knowledge of:

roles and responsibilities of those typically involved in kitchen and bathroom projects, and their involvement at different stages of the project, including at least 7 of the following:

architects

colour consultants

designers

material and component suppliers

builders

cabinetmakers

electricians

flooring specialists

glaziers

painters

plumbers / gas fitters

stonemasons

tilers

waterproofers

key stages and sequencing of kitchen and bathroom projects and what each stage involves:

concept design

design specification

planning approval

technical site assessment/site measure

demolition

construction:

services

waterproofing

installation

differences between renovation and new build projects

project planning and implementation, including:

sequence of operations

budget

timelines

allocation and delivery of resources

contingencies

features of cabinets and components commonly used in kitchen and bathroom projects, including manufacturing methodologies

supply chains for kitchen and bathroom components and materials.

# Assessment Conditions

Skills must have been demonstrated in the workplace or in a simulated environment that reflects workplace conditions and contingencies. The following conditions must be met for this unit:

use of suitable facilities, equipment and resources, including:

project documentation.

Assessors must satisfy the NVR/AQTF mandatory competency requirements for assessors.

# Links

Companion Volume implementation guides are found in VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=0601ab95-583a-4e93-b2d4-cfb27b03ed73