# MSL916015 Manage complex projects

Release: 1

MSL916015 Manage complex projects

# Modification History

Release 1. Supersedes and equivalent to MSL916010 Manage complex projects. Minor wording changes in Performance Criteria and Knowledge Evidence.

# Application

This unit of competency describes the skills and knowledge to interpret complex project briefs, determine project methodologies and resource requirements, establish project plans, manage projects to successful conclusions and evaluate project outcomes.

This unit applies to senior technical officers and laboratory supervisors working in all industry sectors.

No licensing or certification requirements exist at the time of publication. However, regulations and/or external accreditation requirements for laboratory operations exist, so local requirements should be checked. Relevant legislation, industry standards and codes of practice within Australia must also be applied.

# Pre-requisite Unit

Nil.

# Competency Field

Communication/organisation

# Elements and Performance Criteria

| Elements | Performance Criteria |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Interpret brief and design feasible project plan | 1.1 Interpret and confirm project objectives, deliverables, constraints and principal work activities 1.2 Determine resource requirements, including personnel, equipment and materials, and access to operational systems 1.3 Develop a detailed implementation plan for the project outlining methodology, milestones and budget 1.4 Identify roles, responsibilities and required capabilities of project team members 1.5 Analyse project plan and principal work activities to ensure compliance with relevant standards 1.6 Develop risk management strategies and risk management plans to ensure successful and timely outcomes 1.7 Secure project approval in accordance with workplace procedures |
| 2. Establish and implement approved project plan | 2.1 Secure team members and brief them about the project and allocate roles and responsibilities, balancing job roles and skills development opportunities 2.2 Secure necessary equipment, materials and access to operational systems in accordance with plan 2.3 Establish agreed communication and reporting mechanisms 2.4 Implement agreed time-management strategies to ensure milestones are met 2.5 Apply agreed quality requirements to measure performance and outcomes |
| 3. Manage project | 3.1 Monitor and report progress of activities in relation to the project plan 3.2 Ensure income and expenditure is in line with the agreed project plan and budget 3.3 Work with the team to analyse and diagnose problems and to determine corrective actions 3.4 Make agreed variations to the plan to suit changing situations 3.5 Maintain accurate records and communication with stakeholders and project team members |
| 4. Finalise project | 4.1 Ensure project objectives are met and deliverables are provided on time and within budget 4.2 Complete all reporting requirements |
| 5. Evaluate project methodology | 5.1 Assess the effectiveness of resource management in delivering project outcomes 5.2 Evaluate the effectiveness of communication processes used throughout the project 5.3 Recommend improvements for future projects based on evaluation |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance.

Foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Unit Mapping Information

Supersedes and is equivalent to MSL916010 Manage complex projects.

# Links

MSL Laboratory Operations Companion Volume Implementation Guide is available from VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5c63a03b-4a6b-4ae5-9560-1e3c5f462baa

Assessment Requirements for MSL916015 Manage complex projects

# Modification History

Release 1. Supersedes and equivalent to MSL916010 Manage complex projects. Minor wording changes in Performance Criteria and Knowledge Evidence.

# Performance Evidence

There must be evidence the candidate has completed the tasks outlined in the elements and performance criteria of this unit, and:

effectively managed at least 1 complex project to achieve objectives outlined in project plan, on time and within budget constraints.

# Knowledge Evidence

There must be evidence the candidate has knowledge of:

•	types of complex projects that occur in a laboratory, including:

development or modification of products and services

acquisition and commissioning of new equipment or laboratory facilities

implementation of new or updated laboratory software

development of applications for customers

validation of analytical methods and/or equipment

restructuring of laboratory services

reclassification of staff and staffing levels

how the project fits in with the laboratory’s business goals and key performance indicators (KPIs)

legal, ethical and work health and safety (WHS) considerations for management of the project

principles and techniques of project planning and management, including those related to:

project establishment and key inclusions in a project plan

monitoring timelines, expenditure and team performance

achieving effective communication and cooperation

troubleshooting, problem solving and conflict resolution

reporting

evaluation and continuous improvement.

# Assessment Conditions

Skills must have been demonstrated in the workplace or in a simulated environment that reflects workplace conditions and contingencies. The following conditions must be met for this unit:

use of suitable facilities, equipment and resources, including:

a complex project brief

workplace project management processes and procedures

modelling of industry operating conditions, including:

interactions with laboratory work team/s.

Assessors must satisfy the NVR/AQTF mandatory competency requirements for assessors.

# Links

MSL Laboratory Operations Companion Volume Implementation Guide is available from VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5c63a03b-4a6b-4ae5-9560-1e3c5f462baa