# MSS404001 Lead Agile team processes

Release: 1

MSS404001 Lead Agile team processes

# Modification History

Release 1. New unit

# Application

This unit covers the skills and knowledge required to plan for and lead a development team using structured Agile processes to deliver components (or subprojects or increments) of an Agile project.

This unit applies to senior operators, team leaders, managers or others who have been given the responsibility to facilitate communications and collaboration and assist the development team to apply Agile processes to plan and implement iterations.

This unit applies to any organisation that is implementing structured Agile processes.

Agile is typically applied in contexts where the solution or outcome is not known, or in constantly changing environments, and where the customer can reasonably use and critique the ‘product in progress’.

No licensing or certification requirements exist at the time of publication. Relevant legislation, industry standards and codes of practice within Australia must be applied.

# Competency Field

Competitive Systems and Practices

# Elements and Performance Criteria

| Elements | Performance Criteria |  |
| --- | --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |  |
| 1 Contribute to planning of subprojects and iterations |  | 1.1 Liaise with Agile project manager roles to determine subprojects and goals 1.2 Regularly discuss subprojects and work to be done with Agile project manager roles and amend plans accordingly 1.3 Assist in selection and set up of visual indicators to support identification and tracking of project work and processes 1.4 Assist team to determine and plan iterations and acceptance criteria to meet subproject goals |
| 2 Lead Agile team to deliver iterations |  | 2.1 Lead team meetings which support open communications, team decision making and review of outcomes 2.2 Assist team to determine work activities, capacity and timing based on iterations 2.3 Facilitate negotiation of priorities, roles, tasks and workloads within cross functional team 2.4 Promote team commitment to and accountability for work outcomes 2.5 Ensure team maintains discipline in Agile processes and focus on subproject goals 2.6 Facilitate processes to assist team to achieve release of iterations 2.7 Regularly update team on changes to project direction, goals and work priorities 2.8 Recognise skill and/or other development needs for team to work within Agile and provide mentoring or initiate support |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance.

Reading skills to interpret workplace documentation and visual indicators

Oral communication skills to facilitate engagement and participation

Numeracy skills to determine team capacity and tracking of project work.

Other foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Unit Mapping Information

No equivalent unit.

# Links

Companion Volume Implementation Guides are found in VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5b04f318-804f-4dc0-9463-c3fb9a3fe998