# MSS405044 Facilitate Agile projects

Release: 1

MSS405044 Facilitate Agile projects

# Modification History

Release 1. New unit.

# Application

This unit covers the skills and knowledge required to plan and facilitate structured Agile processes to deliver customer value.

This unit applies to senior operators, team leaders, managers or others who have been given the authority to gain input from customers, project partners and others to define the project direction and goals, maintain focus on customer specifications, plan project increments and facilitate project team to deliver increments.

This unit applies to any organisation that is implementing structured Agile processes.

Agile is typically applied in contexts where the solution or outcome is not known, or in constantly changing environments, and where the customer can reasonably use and critique the ‘product in progress’.

No licensing or certification requirements exist at the time of publication. Relevant legislation, industry standards and codes of practice within Australia must be applied.

# Competency Field

Competitive Systems and Practices

# Elements and Performance Criteria

| Elements | Performance Criteria |  |
| --- | --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |  |
| 1 Define Agile project |  | 1.1 Liaise with customer and project partners or stakeholders to determine project direction, objectives and goals relevant to customer specifications 1.2 Plan project increments, testing requirements and metrics to achieve project goals 1.3 Determine planning, prioritisation and decision making frameworks for project |
| 2 Establish project |  | 2.1 Select team members including cross-functional members as relevant to project goals 2.2 Communicate project direction, objectives, goals and work priorities to team 2.3 Guide selection and set up of visual indicators and milestones to support identification and tracking of project work and processes 2.4 Assist team to plan and determine criteria for iterations |
| 3 Maintain focus on customer needs |  | 3.1 Monitor testing and customer feedback to identify need for changes to project direction and/or goals 3.2 Negotiate with customer and project partners or stakeholders to facilitate agreement on changes to direction and/or goals 3.3 Monitor and amend work priorities, with input from customer and project partners or stakeholders 3.4 Define and allocate work required to be done according to project goals and priorities 3.5 Regularly update team on changes to project direction, objectives, goals and work priorities |
| 4 Facilitate Agile values within projects |  | 4.1 Communicate with managers and/or leaders to promote understanding of and commitment to Agile values across organisation 4.2 Facilitate organisational processes to empower project teams and promote open communications and transparency 4.3 Ensure resources and procedures are in place to support incremental and iterative work processes 4.4 Recognise skill and/or other development needs for project partners and team members to work within Agile and provide coaching and mentoring or initiate support |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance.

Reading skills to interpret workplace documentation and visual indicators

Writing skills to document and communicate project plans, goals, increments and metrics

Oral communication skills to facilitate agreement with customers and leadership team, guide others

Numeracy skills to determine metrics.

Other foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Unit Mapping Information

Release 1. No equivalent unit.

# Links

Companion Volume Implementation Guides are found in VETNet – - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=5b04f318-804f-4dc0-9463-c3fb9a3fe998