# PSPPM402B Manage simple projects

Revision Number: 3

PSPPM402B Manage simple projects

# Modification History

| Release | TP Version | Comments |
| --- | --- | --- |
| 3 | PSP12V1 | Unit descriptor edited. |
| 2 | PSP04V4.2. | Layout adjusted. No changes to content. |
| 1 | PSP04V4.1 | Primary release. |

# Unit Descriptor

This unit covers management of generally low risk projects that may be small scale and managed by one person or a person with a small team. It includes implementing project start-up activities, coordinating project implementation, monitoring the project and arranging follow-up activities. Contract management requirements are not included as this aspect is addressed by units of competency within the Competency field of Procurement and Contract Management.

In practice, managing simple projects overlaps with other generalist and specialist work activities such as applying government processes, using resources, gathering information, managing contracts etc.

This unit, and unit PSPPM405A Administer simple projects, are mutually exclusive. One or the other, but not both, may contribute to a qualification.

No licensing, legislative, regulatory or certification requirements apply to this unit at the time of publication

# Application of the Unit

Not applicable.

# Licensing/Regulatory Information

Not applicable.

# Pre-Requisites

Not applicable.

# Employability Skills Information

This unit contains employability skills.

# Elements and Performance Criteria Pre-Content

| Elements are the essential outcomes of the unit of competency. | Together, performance criteria specify the requirements for competent performance. Text in bold italics is explained in the Range Statement following. |
| --- | --- |

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| 1. Implement start-up activities | 1.1 The project plan is updated with confirmed information for key dates and activities, resources and project governance details in accordance with the project implementation strategy. 1.2 Project stakeholders' understanding of and agreement to fulfil the project requirements and their roles and responsibilities are confirmed. 1.3 Required systems are established and maintained throughout the project in accordance with the project plan. 1.4 A working knowledge of project management tools is used to facilitate integration of project activities and achievement of project outcomes. |
| 2. Coordinate project implementation | 2.1 Integration and management of project activities are handled in accordance with the project plan. 2.2 Stakeholder input and expectations are managed and their commitment is maintained throughout the life of the project in accordance with organisational policy and procedures and the project plan. 2.3 Disagreements and disputes are resolved or referred to a higher authority in accordance with organisational policy and procedures. 2.4 Project change proposals are received and changes are recommended/made in accordance with the project plan, and documented in accordance with policy and procedures. |
| 3. Monitor project | 3.1 All aspects of the project are continually monitored and corrective action is taken as necessary to maintain progress in accordance with the project plan. 3.2 Consultation and reporting mechanisms are applied in accordance with the communication plan when dealing with management, staff and/or contractors, steering committee members or other stakeholders. 3.3 Project governance plans and any related contracts are monitored, reviewed and amended as appropriate, and results are reported in accordance with the communication plan. 3.4 Project progress is monitored against agreed milestones in accordance with the project plan to provide a measure of performance throughout the life of the contract. 3.5 Programmed review of objectives and achievement is implemented in accordance with the project plan. |
| 4. Arrange project follow-up activities | 4.1 Project deliverables are analysed against specifications, performance standards and project objectives, under broad guidance, and the results are reported to stakeholders. 4.2 An initial support package or product manual is produced, if required, to provide guidance for stakeholders who will be required to apply the project results. 4.3 The support package includes options for stakeholders to take account of environmental and cultural factors in applying project results. 4.4 Operational and support authorities are consulted to research any testing/trialling/building requirements resulting from the project, and evaluation of any recommendations are included in the project report. |

# Required Skills and Knowledge

This section describes the essential skills and knowledge and their level, required for this unit.

Skill requirements Look for evidence that confirms skills in: leading and mentoring people to achieve project deliverables maintaining agreement of stakeholders and team members to timelines, roles and responsibilities communicating with stakeholders and team members using a range of communication styles to suit different audiences and purposes responding to diversity, including gender and disability using project management tools applicable to small scale or low risk projects applying ethical decision making and problem solving related to project management of small scale or low risk projects writing recommendations and preparing implementation support packages requiring precision of expression applying workplace safety procedures in line with project requirements accessing/preparing information electronically or in hard copy

Knowledge requirements Look for evidence that confirms knowledge and understanding of: legislation, organisational policies and procedures that may impact on project management, for example: public sector codes of ethics/conduct occupational health and safety and environment requirements project governance requirements quality standards risk management procurement guidelines human resources equal employment opportunity, equity and diversity principles project management tools to suit a range of small scale or low risk projects project management principles organisational and political context

# Evidence Guide

| The Evidence Guide specifies the evidence required to demonstrate achievement in the unit of competency as a whole. It must be read in conjunction with the Unit descriptor, Performance Criteria, the Range Statement and the Assessment Guidelines for the Public Sector Training Package. |  |
| --- | --- |
| Units to be assessed together | Pre-requisite units that must be achieved prior to this unit:Nil Co-requisite units that must be assessed with this unit:Nil Co-assessed units that may be assessed with this unit to increase the efficiency and realism of the assessment process include, but are not limited to: PSPETHC401A Uphold and support the values and principles of public service PSPGOV402B Deliver and monitor service to clients PSPGOV403B Use resources to achieve work unit goals PSPGOV411A Deal with conflict PSPGOV412A Use advanced workplace communication strategies PSPGOV422A Apply government processes PSPLEGN401A Encourage compliance with legislation in the public sector PSPPROC410A Administer contracts PSPPM401B Design simple projects PSPPM403B Close simple projects Excluded units that may not contribute to the same qualification as this unit: PSPPM405A Administer simple projects |
| Overview of evidence requirements | In addition to integrated demonstration of the elements and their related performance criteria, look for evidence that confirms: the knowledge requirements of this unit the skill requirements of this unit application of the Employability Skills as they relate to this unit (see Employability Summaries in Qualifications Framework) simple projects managed in a range of (3 or more) contexts (or occasions, over time) |
| Resources required to carry out assessment | These resources include: legislation, guidelines, procedures and protocols relating to project management workplace project documentation scenarios and case studies examples of project management tools |
| Where and how to assess evidence | Valid assessment of this unit requires: a workplace environment or one that closely resembles normal work practice and replicates the range of conditions likely to be encountered when implementing projects, including coping with difficulties, irregularities and breakdowns in routine simple projects managed in a range of (3 or more) contexts (or occasions, over time) Assessment methods should reflect workplace demands, such as literacy, and the needs of particular groups, such as: people with disabilities people from culturally and linguistically diverse backgrounds Aboriginal and Torres Strait Islander people women young people older people people in rural and remote locations Assessment methods suitable for valid and reliable assessment of this competency may include, but are not limited to, a combination of 2 or more of: case studies demonstration portfolios questioning scenarios authenticated evidence from the workplace and/or training courses |
| For consistency of assessment | Evidence must be gathered over time in a range of contexts to ensure the person can achieve the unit outcome and apply the competency in different situations or environments |

# Range Statement

| The Range Statement provides information about the context in which the unit of competency is carried out. The variables cater for differences between States and Territories and the Commonwealth, and between organisations and workplaces. They allow for different work requirements, work practices and knowledge. The Range Statement also provides a focus for assessment. It relates to the unit as a whole. Text in bold italics in the Performance Criteria is explained here. |  |
| --- | --- |
| Project plan will include some or all of: | acquisition strategies budget and financial management strategy contract management cost estimates evaluation criteria expected outcomes/measurable benefits of the project facilities inclusions and exclusions from project information/communication strategy intellectual property strategies milestones objectives outputs/project deliverables and their acceptance criteria people plan including human resource management and human resource development performance criteria/indicators project control mechanisms project implementation strategy project governance strategy purpose quality assurance quality control quality standards for project rationale required project resources resource management risk management roles and responsibilities schedule/timeline task/work breakdown structure (WBS) |
| Stakeholders may include: | project sponsor/funding bodies clients or customers (internal and external) industry other agencies general public relevant interest groups unions functional areas the organisation's senior management Ministers project team steering committee members end user supplier/service provider |
| Required systems for project management may include: | planning and monitoring system financial management including: budget allocation/funding income generated expenditure recordkeeping for documented information such as: correspondence quality data including survey, needs, test results contracts time allocated and spent on each aspect of the project progress reports performance reports against milestones project outcomes samples, prototypes, models |
| Project management tools may include: | risk analysis organisational project governance framework communications plan reporting framework project management software and other tools: Gantt and bar charts Program Evaluation and Review Technique (PERT) charts Critical Path Method cost schedule control system logistics support analysis life cycle cost analysis spreadsheets recording systems - electronic and manual |
| Integration of project activities may include: | scope time cost quality human resources communications risk procurement |
| Management may include: | scope management communication and reporting schedule management financial management quality management resources management people management logistics management risk management contract management change management |
| Change proposals may include: | scope administration engineering, technical, technology changes time cost resources |
| Policy and procedures may include: | government legislation (Federal, State and Local) affecting organisation's administration such as: public sector management acts financial management and accounting legislation and regulations privacy legislation government and organisational guidelines and procedures relating to: project governance resourcing security strategic plans recruitment risk management procurement guidelines designation approvals industrial agreements |
| Specifications may include: | functional technical performance material |

# Unit Sector(s)

Not applicable.

# Competency field

Project Management.