# Assessment Requirements for PUARCV006 Coordinate recovery activities across recovery environments

Release: 1

Assessment Requirements for PUARCV006 Coordinate recovery activities across recovery environments

# Modification History

Release 1. This is the first release of this unit of competency in the PUA Public Safety Training Package.

# Performance Evidence

Evidence required to demonstrate competence in this unit must be relevant to and satisfy all of the requirements of the elements and performance criteria on at least one occasion and include:

coordinating recovery operations consisting of a plan that includes: human and equipment resources hazard and impact data analysis community needs assessment data relief and evacuation recovery resources deployment strategies public information arrangements through ongoing consultation communication strategies preparing reports which include budget expenditure stakeholder networks and communication channels reporting on recovery programs and expenditure in accordance with organisational and recovery arrangements concluding the recovery arrangements producing a transition plan coordinating recovery operations across recovery environments for at least one disaster event conducting an end of program evaluation report using approved methodology developing an evaluation and monitoring process targeting the assessment of the agreed outcomes implementing recovery management processes consisting of: activating a recovery coordination facility establishing a recovery team structure community engagement and communication arrangements monitoring and evaluating frameworks developing and implementing a recovery management plan obtaining and recording details of disaster-impacted community working with other relevant stakeholders to coordinate recovery needs.

# Knowledge Evidence

Evidence required to demonstrate competence in this unit must be relevant to and satisfy all of the requirements of the elements and performance criteria and include knowledge of:

communication channels appropriate to recovery activities across recovery environments disaster and recovery arrangements disaster welfare services, processes and practices disaster recovery funding arrangements recovery data sources and analysis key recovery stakeholders lessons learnt information management management functions of recovery monitoring and evaluation methods overlapping short, medium and long-term priorities recovery principles and recovery environments recovery arrangements recovery environments recovery stakeholder networks recovery transition planning and processes recovery team structures recovery resources services provided in evacuation, relief and recovery centres and outreach teams support services available for long-term recovery.

# Assessment Conditions

Assessors must hold credentials specified within the Standards for Registered Training Organisations current at the time of assessment. Assessment must satisfy the Principles of Assessment and Rules of Evidence and all regulatory requirements included within the Standards for Registered Training Organisations current at the time of assessment. Assessment must occur in workplace operational situations. Where this is not appropriate, assessment must occur in simulated workplace operational situations that reflect workplace conditions. Assessment processes and techniques must be appropriate to the language, literacy and numeracy requirements of the work being performed and the needs of the candidate. Resources for assessment must include access to: a range of relevant exercises, case studies and/or simulations applicable documentation, including workplace procedures, regulations, codes of practice and operation manuals relevant materials, tools, equipment and personal protective equipment (PPE) currently used in industry.

# Links

Companion Volume Implementation Guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=3eca5672-6d5a-410b-8942-810d0ba05bbf