# RIICSG406E Supervise maintenance of civil structures

Release: 1

RIICSG406E Supervise maintenance of civil structures

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with RII Resources and Infrastructure Industry Training Package Version 6.0. |

# Application

This unit describes the skills and knowledge required supervise maintenance of civil structures, including implementing the job plan and overseeing and reporting on the execution of civil structure maintenance tasks.

It applies to those working in supervisory or technical specialist roles. They generally perform a broad range of operational activities in their area of responsibility and are responsible for monitoring a safe work environment.

Licensing, legislative and certification requirements that apply to this unit can vary between states, territories, and industry sectors. Users must check requirements with relevant body before applying the unit.

# Unit Sector

Civil construction

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Plan and prepare tasks | 1.1 Obtain, interpret and clarify work requirements 1.2 Access, interpret and apply documentation required to supervise maintenance of civil structures and confirm work activity is compliant 1.3 Identify and address potential risks, hazards and environmental issues and implement control measures 1.4 Select and wear personal protective equipment according to site requirements 1.5 Prepare and implement a job plan that meets task requirements in consultation with team members 1.6 Confirm required resources are acquired and made available for task |
| 2. Prepare team members to execute tasks | 2.1 Identify team member training requirements and develop and implement training plans 2.2 Issue task instructions to team members and others involved according to job requirements |
| 3. Oversee execution of tasks | 3.1 Monitor civil structures maintenance task performance 3.2 Implement adjustments to work processes and job plan as required and confirm required outcomes are achieved 3.3 Confirm program for plant, equipment and tool maintenance is carried out and written records are kept |
| 4. Report on execution of tasks | 4.1 Complete and submit reports according to site requirements 4.2 Recommend changes to improve maintenance of civil structures |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Numeracy | Calculates basic measurements including mass and dimensions |
| Oral communication | Presents training plans and task instructions to a group using sector-specific vocabulary |
| Writing | Writes training plans, job plans and workplace reports and recommendations considering available resources and time frames |

# Unit Mapping Information

Supersedes and is equivalent to RIICSG406D Apply principles of maintenance of civil structures.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=88a61002-9a21-4386-aaf8-69c76e675272