# Assessment Requirements for RIICWM401E Supervise civil works

Release: 1

Assessment Requirements for RIICWM401E Supervise civil works

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with RII Resources and Infrastructure Industry Training Package Version 6.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

supervise civil works on at least two occasions, including:

preparing at least one job plan, including:

human resource requirements

plant and machinery requirements

construction materials requirements

sub-contractor support requirements

waste disposal requirements

coordination requirements

activity scheduling

materials delivery scheduling

risk assessment and management requirements

occupational health and safety requirements

quality management requirements, including testing scheduling requirements

traffic management requirements

environmental requirements

task monitoring requirements

task performance monitoring requirements

communication requirements

reporting requirements

monitoring each of the following:

ongoing risk assessment

engineering survey

sampling and testing

recording and observation of construction practice

providing general supervision.

During the above, the candidate must:

locate and apply required legislation, documentation, policies and procedures

work with others to supervise civil works that meets required outcomes, including:

organising work activities to meet task requirements

communicating with others to receive and clarify work instructions

communicating with others to resolve coordination requirements prior to commencing and during work activities.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

legislation required to supervise civil works

policies, procedures and documentation required to supervise civil works, including those related to:

risk assessment and management

work health and safety

emergency response

environmental management

workplace recording and reporting requirements, including:

task specifications

job plan

task drawings

activity scheduling

waste management

materials delivery scheduling

task monitoring

manufacturer specifications for relevant plant and equipment

traffic management requirements

developing of job plans

types, characteristics, technical capabilities and limitations of materials, plant and equipment required to supervise civil works

relationship between various areas of civil works

principles and techniques required to supervise civil works, including those relating to:

team leadership

works planning

civil works monitoring

engineering survey principles

estimating principles

civil works construction sequencing

sampling and testing

set out requirements and procedures

road geometry

drainage requirements.

# Assessment Conditions

Mandatory conditions for assessment of this unit are stipulated below. The assessment must:

include access to:

personal protective equipment

equipment required to supervise civil works

be conducted in a safe environment; and,

be assessed in the context of this sector’s work environment; and,

be assessed in compliance with relevant legislation/regulation and using policies, procedures and processes directly related to the industry sector for which it is being assessed; and,

confirm consistent performance can be applied in a range of relevant workplace circumstances.

Where personal safety or environmental damage are limiting factors, assessment may occur in a simulated work environment* provided it is realistic and sufficiently rigorous to cover all aspects of this sector’s workplace performance, including environment, task skills, task management skills, contingency management skills and job role environment skills.

Assessor requirements

Assessors must be able to clearly demonstrate current and relevant industry knowledge and experience to satisfy the mandatory regulatory standards as set out in the Standards for Registered Training Organisations 2015/Australian Quality Training Framework mandatory requirements for assessors current at the time of assessment and any relevant licensing and certification requirements. This includes:

vocational competencies at least to the level being delivered and assessed

current industry skills directly relevant to the training and assessment being provided

current knowledge and skills in vocational training and learning that informs their training and assessment

formal relevant qualifications in training and assessment

having knowledge of and/or experience using the latest techniques and processes

possessing the required level of RII training product knowledge

having an understanding and knowledge of legislation and regulations relevant to the industry and to employment and workplaces

demonstrating the performance evidence, and knowledge evidence outlined in this unit of competency, and

the minimum years of current** work experience after competency has been obtained as specified below in an industry sector relevant to the outcomes of the unit.

It is also acceptable for the appropriately qualified assessor to work with an industry expert to conduct assessment together and for the industry expert to be involved in the assessment judgement. The industry expert must have current industry skills directly relevant to the training and assessment being provided. This means the industry subject matter expert must demonstrate skills and knowledge from the minimum years of current work experience after competency has been obtained as specified below, including time spent in roles related to the unit being assessed:

| #### Industry sector | #### AQF indicator level*** | #### Required assessor or industry subject matter expert experience |
| --- | --- | --- |
| Drilling, Metalliferous Mining, Coal Mining, Extractive (Quarrying) and Civil Infrastructure | 1 | 1 year |
|  | 2 | 2 years |
| Drilling, Coal Mining, Extractive (Quarrying), Metalliferous Mining and Civil Infrastructure | 3-6 | 3 years |
| Other sectors | Where this unit is being assessed outside of the resources and infrastructure sectors assessor and/or industry subject matter expert experience should be in-line with industry standards for the sector in which it is being assessed and where no industry standard is specified should comply with any relevant regulation. |  |

*Guidance on simulated environments has been stipulated in the Companion Volume Implementation Guide located on VETNet.

**Assessors can demonstrate current work experience through employment within industry in a role relevant to the outcomes of the unit; or, for external assessors this can be demonstrated through exposure to industry by conducting a minimum number of site assessments as determined by the relevant industry sector, across various locations.

*** While a unit of competency does not have an AQF level, where a unit is being delivered outside of a qualification the first numeric character in the unit code should be considered as the AQF indicator level for assessment purposes.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=88a61002-9a21-4386-aaf8-69c76e675272