# RIICWM402E Supervise civil works contractors

Release: 1

RIICWM402E Supervise civil works contractors

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with RII Resources and Infrastructure Industry Training Package Version 6.0. |

# Application

This unit describes the skills and knowledge required to supervise civil works contractors in civil construction, including confirming the initiation of, overseeing and reporting on civil works contractor performance.

It applies to those working in supervisory roles, or in technical specialist roles. They generally perform a broad range of operational activities in their area of responsibility and are responsible for monitoring a safe work environment.

Licensing, legislative and certification requirements that apply to this unit can vary between states, territories, and industry sectors. Users must check requirements with relevant body before applying the unit.

# Unit Sector

Civil construction

# Elements and Performance Criteria

| ELEMENT | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Plan and prepare to supervise contractors of civil works | 1.1 Obtain, interpret and confirm work requirements 1.2 Access, interpret and apply documentation required to supervise civil works contractors and confirm work activity is compliant 1.3 Identify and address potential risks, hazards and environmental issues and implement control measures 1.4 Select and wear personal protective equipment according to site requirements 1.5 Confirm contractor has a job plan available that meets task requirements 1.6 Confirm required resources are acquired and made available for task |
| 2. Confirm task initiation | 2.1 Confirm contractor has communicated instructions to team members and others involved 2.2 Set out tasks as required for completion of civil works |
| 3. Oversee execution of tasks | 3.1 Monitor civil works contractor performance and confirm required outcomes are achieved 3.2 Implement adjustments to civil works practice and job plan as required 3.3 Confirm plant, equipment and tool maintenance requirements are carried out and recorded |
| 4. Report on execution of tasks | 4.1 Complete and submit reports according to site requirements 4.2 Recommend improvements to civil works practice |

# Foundation Skills

This section describes those language, literacy, numeracy and employment skills that are essential to performance but not explicit in the performance criteria.

| Skill | Description |
| --- | --- |
| Oral communication | Presents workplace procedures and technical instructions using sector-specific vocabulary |

# Unit Mapping Information

Supersedes and is equivalent to RIICWM402D Supervise civil works contractors.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=88a61002-9a21-4386-aaf8-69c76e675272

Assessment Requirements for RIICWM402E Supervise civil works contractors

# Modification History

| Release | Comments |
| --- | --- |
| Release 1 | This version first released with RII Resources and Infrastructure Industry Training Package Version 6.0. |

# Performance Evidence

The candidate must demonstrate the ability to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including evidence of the ability to:

supervise civil works contractors on at least two occasions, including:

preparing a job plan that is to include:

human resource requirements

plant and machinery requirements

construction materials requirements

sub-contractor support requirements

waste disposal requirements

coordination requirements

activity scheduling

materials delivery scheduling

risk assessment and management requirements

work health and safety requirements

quality management requirements, including testing scheduling requirements

traffic management requirements

environmental requirements

task monitoring requirements

task performance monitoring requirements

communication requirements

reporting requirements

performing ongoing risk assessment

interpreting engineering surveys

performing sampling and testing and interpreting results

recording and observing construction practice

providing general supervision.

During the above, the candidate must:

locate and apply required legislation, documentation, policies and procedures

implement procedures and techniques for the supervision of civil works contractors, including accessing, interpreting and applying:

project site soil and geological data

meteorological data

material properties and test results, including compaction test results

project site geotechnical data

project site hydrological data

work with others to supervise civil works contractors that meets required outcomes, including:

organising work activities to meet task requirements

communicating with others to receive and clarify work instructions

communicating with others to resolve coordination requirements prior to commencing and during work activities

consulting with stakeholders.

# Knowledge Evidence

The candidate must be able to demonstrate knowledge to complete the tasks outlined in the elements, performance criteria and foundation skills of this unit, including knowledge of:

legislation required to supervise civil works contractors

policies, procedures and documentation required to supervise civil works contractors, including those relating to:

risk assessment and management

statutory compliance

work health and safety

emergency response

environmental management

quality management

work zone traffic management

contract management

specifications

organisational and site operational requirements

materials quality and delivery

coordination, timing and budgeting

cultural and heritage management

assessment of operational techniques

assessment of resource requirements

workplace reporting requirements, including:

task specifications

job plan

task drawings

activity scheduling

unit costs

overall task costs

workplace roles and responsibilities

relationship between various areas of civil works

civil works plant and equipment capabilities and limitations, including maintenance requirements

principles and techniques required to supervise civil works contractors, including those relating to:

civil works tasks

task specific information and requirements, including:

site geological, geotechnical, hydrological and meteorological data

job plan development

civil works construction sequencing

civil works monitoring

engineering survey principles

set out requirements and procedures

road geometry

materials properties and test results, including compaction test results

drainage requirements.

# Assessment Conditions

Mandatory conditions for assessment of this unit are stipulated below. The assessment must:

include access to:

personal protective equipment

equipment required to supervise civil works contractors

be conducted in a safe environment; and,

be assessed in the context of this sector’s work environment; and,

be assessed in compliance with relevant legislation/regulation and using policies, procedures and processes directly related to the industry sector for which it is being assessed; and,

confirm consistent performance can be applied in a range of relevant workplace circumstances.

Where personal safety or environmental damage are limiting factors, assessment may occur in a simulated work environment* provided it is realistic and sufficiently rigorous to cover all aspects of this sector’s workplace performance, including environment, task skills, task management skills, contingency management skills and job role environment skills.

Assessor requirements

Assessors must be able to clearly demonstrate current and relevant industry knowledge and experience to satisfy the mandatory regulatory standards as set out in the Standards for Registered Training Organisations 2015/Australian Quality Training Framework mandatory requirements for assessors current at the time of assessment and any relevant licensing and certification requirements. This includes:

vocational competencies at least to the level being delivered and assessed

current industry skills directly relevant to the training and assessment being provided

current knowledge and skills in vocational training and learning that informs their training and assessment

formal relevant qualifications in training and assessment

having knowledge of and/or experience using the latest techniques and processes

possessing the required level of RII training product knowledge

having an understanding and knowledge of legislation and regulations relevant to the industry and to employment and workplaces

demonstrating the performance evidence, and knowledge evidence outlined in this unit of competency, and

the minimum years of current** work experience after competency has been obtained as specified below in an industry sector relevant to the outcomes of the unit.

It is also acceptable for the appropriately qualified assessor to work with an industry expert to conduct assessment together and for the industry expert to be involved in the assessment judgement. The industry expert must have current industry skills directly relevant to the training and assessment being provided. This means the industry subject matter expert must demonstrate skills and knowledge from the minimum years of current work experience after competency has been obtained as specified below, including time spent in roles related to the unit being assessed:

| #### Industry sector | #### AQF indicator level*** | #### Required assessor or industry subject matter expert experience |
| --- | --- | --- |
| Drilling, Metalliferous Mining, Coal Mining, Extractive (Quarrying) and Civil Infrastructure | 1 | 1 year |
|  | 2 | 2 years |
| Drilling, Coal Mining, Extractive (Quarrying), Metalliferous Mining and Civil Infrastructure | 3-6 | 3 years |
| Other sectors | Where this unit is being assessed outside of the resources and infrastructure sectors assessor and/or industry subject matter expert experience should be in-line with industry standards for the sector in which it is being assessed and where no industry standard is specified should comply with any relevant regulation. |  |

*Guidance on simulated environments has been stipulated in the Companion Volume Implementation Guide located on VETNet.

**Assessors can demonstrate current work experience through employment within industry in a role relevant to the outcomes of the unit; or, for external assessors this can be demonstrated through exposure to industry by conducting a minimum number of site assessments as determined by the relevant industry sector, across various locations.

*** While a unit of competency does not have an AQF level, where a unit is being delivered outside of a qualification the first numeric character in the unit code should be considered as the AQF indicator level for assessment purposes.

# Links

Companion Volume Implementation Guide is found on VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=88a61002-9a21-4386-aaf8-69c76e675272