# SISXFAM006 Coordinate sport, fitness or recreation events

Release: 1

SISXFAM006 Coordinate sport, fitness or recreation events

# Modification History

Not applicable.

# Application

This unit describes the performance outcomes, skills and knowledge required to coordinate the planning and delivery of sport, fitness, aquatic or recreation events at a single site or venue. It covers skills for completing the advance planning of all event components, coordinating the on-site set-up and break-down of events, supervising on-site event operations and the event team, and evaluating effectiveness of operational practices.

This unit applies to any type of sport, fitness, aquatic or recreation organisation including commercial, not-for-profit, community and government organisations. It applies to event coordinators and managers as well as venue and operations managers who operate independently, and who are responsible for operational decisions.

The skills in this unit must be applied in accordance with Commonwealth and State or Territory legislation, Australian standards and industry codes of practice.

No occupational licensing, certification or specific legislative requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Competency Field

Finance, Administration and Marketing

# Unit Sector

Cross-Sector

# Elements and Performance Criteria

| ELEMENTS | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes. | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Identify scope of the event. | 1.1. Analyse event information to confirm purpose, objectives and overall budget for event. 1.2. Determine event components and create overall schedule to facilitate operational planning. 1.3. Determine and accurately document specific venue, staging and human resource requirements to facilitate event planning and service bookings. |
| 2. Plan event operation. | 2.1. Develop and document draft and finalised event running sheets incorporating event components, tasks, responsibilities and timelines. 2.2. Issue initial and finalised event orders to internal personnel and external suppliers, incorporating specifications for service provision. 2.3. Prepare and distribute finalised event program and attendee documents to publicise event. 2.4. Establish event delivery team and clarify roles and responsibilities. 2.5. Identify event specific risks and develop responsive contingency management plans. 2.6. Monitor event budget and preparations through ongoing liaison with internal personnel and external suppliers, and make required adjustments to event plans. 2.7. Prepare and distribute final operational documents to event delivery teams, internal personnel and external suppliers, incorporating agreed specifications for operation of event. |
| 3. Coordinate on-site set-up, operation and break-down of event. | 3.1. Provide briefing for event operation to internal and external delivery personnel, inclusive of communication and reporting mechanisms. 3.2. Oversee and assess event set-up against prearranged operational specifications. 3.3. Monitor event operation through observation and communication with relevant personnel. 3.4. Identify, evaluate and take prompt action to resolve arising problems. 3.5. Oversee event break-down and ensure completion according to agreed arrangements with team members and external suppliers. |
| 4. Evaluate operational success of event. | 4.1. Obtain feedback from attendees and seek input from personnel and suppliers on event operations. 4.2. Reflect on and evaluate operational problems. 4.3. Provide recommendations for future improvements to operational practices. |

# Foundation Skills

| Foundation skills essential to performance in this unit, but not explicit in the performance criteria are listed here, along with a brief context statement. |  |
| --- | --- |
| SKILLS | DESCRIPTION |
| Reading skills to: | interpret unfamiliar and complex information in event outlines and supplier product specifications. |
| Writing skills to: | develop complex and varied documentation in a format and style suited to purpose and audience need. |
| Oral communication skills to: | provide clear and unambiguous instructions to event team members and suppliers before and during event operation. |
| Numeracy skills to: | interpret diverse components of event budgets to develop operational specifications within budgetary parameters work quickly with budget figures to calculate effect on event costs when resolving on-site problems. |
| Problem-solving skills to: | negotiate solutions with attendees and event personnel under pressure where time constraints play a key factor. |

# Unit Mapping Information

Supersedes and is not equivalent to SISXIND006 Conduct sport, fitness or recreation events.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1ca50016-24d2-4161-a044-d3faa200268b

Assessment Requirements for SISXFAM006 Coordinate sport, fitness or recreation events

# Modification History

Not applicable.

# Performance Evidence

Evidence of the ability to complete tasks outlined in elements and performance criteria of this unit in the context of the job role, and:

plan the operation of two single-site sport, fitness, aquatic or recreation events

for each of the above two events, develop accurate and comprehensive:

operational planning documents

attendee documents

operational staging documents

coordinate the on-site set-up, operation and break-down of one of the above planned events, and:

evaluate the operational effectiveness of the event

document details of the evaluation including recommendations for future improvements to event operations.

# Knowledge Evidence

Demonstrated knowledge required to complete the tasks outlined in elements and performance criteria of this unit:

characteristics, components, and running formats of events commonly operated by sport, fitness, aquatic and recreation organisations:

fundraisers

competitions

awards presentations

open days to promote service offerings

member social events

key features of event staging products and services:

catering

talent:

compere

speakers

entertainers

technical equipment and services:

audio visual

lighting

sound

venue or site:

layouts

styling

displays, stands and signage

entrance and registration areas and equipment

security

common risks associated with event operations, typical contingency plans used to manage these, and how to manage circumstances when they arise:

over or under subscription to event activities

no-show, or lateness of event team members, external suppliers and speakers

injury or illness of attendees and event team members

adverse weather for outdoor events

equipment break-down

environmental and social sustainability considerations and practices for event operation:

recycling and disposing of waste

use of energy, water and other resources

reducing impacts on neighbouring residents

roles and responsibilities of those involved in event planning and staging:

event coordinators and managers

internal event team members, including volunteers

external venue personnel

external service providers

team structure for instructions, reporting and resolution of problems during event operation

communication methods and equipment used between event coordinators and event team during event operation

purpose, inclusions and formats for a diverse range of event documentation:

operational planning documents:

event budgets

overarching schedule of event components

draft running sheets

event orders for internal departments and external suppliers

risk assessment and contingency management plan

attendee documents:

event program

costs and registration details

invoices, receipts and confirmation documents

competition draw

operational staging documents:

site or venue layout and styling, and details of displays, stands, signage, technical and other equipment

finalised running sheets for set-up, operation and break-down of all event components inclusive of timing and event team responsibilities

competition schedules and competitor draw

scripts or speaking outlines for compere and speakers

methods used for the evaluation of events:

debriefs and discussions with event team members

discussions with external venue operators and suppliers

attendee evaluation questionnaires and on-site discussions

evaluation of complaints, problems or difficulties.

# Assessment Conditions

Skills for coordinating on-site event operations must be demonstrated during the staging of a sport, fitness, aquatic or recreation event in live time where realistic time pressures and constraints play a key factor. This can be:

an actual industry event, or

a simulated industry event set up for the purpose of skills assessment.

Assessment must ensure use of:

interaction with event team members and suppliers; these can be:

team members and suppliers in an industry workplace, or

individuals who participate in simulated activities used for the purpose of skills assessment

event:

budgets

operational planning documents

attendee documents

operational staging documents.

Assessors must satisfy the Standards for Registered Training Organisations’ requirements for assessors.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=1ca50016-24d2-4161-a044-d3faa200268b