# SITEEVT028 Manage on-site event operations

Release: 1

SITEEVT028 Manage on-site event operations

# Modification History

Not applicable.

# Application

This unit describes the performance outcomes, skills and knowledge required to manage on-site operational activities for the production of events. It requires the ability to finalise operational plans, oversee event set-up, execution and break-down, and evaluate the operational success of events.

This unit is relevant to events that are diverse in nature and are coordinated in many industry contexts, including the tourism, hospitality, sport, cultural and community sectors.

It applies to event coordinators and managers as well as venue duty, front of house and operations managers who operate independently, and are responsible for operational decisions. They may work in event management companies, in event venues, or in organisations that organise their own events.

The skills in this unit of competency must be applied in accordance with Commonwealth and State/Territory legislation, Australian standards and industry codes of practice.

No occupational licensing, certification or specific legislative requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Competency Field

# Unit Sector

Events

# Elements and Performance Criteria

| ELEMENTS | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Finalise event preparations. | 1.1. Check final arrangements for event and address discrepancies or outstanding matters. 1.2. Analyse event requirements and develop plans and procedures for event production. 1.3. Prepare and collate operational documentation to facilitate effective on-site management and distribute to relevant personnel. 1.4. Develop and provide event briefings to relevant personnel in advance of event. 1.5. Minimise use of printed materials and maximise electronic transmission of documents to reduce waste. |
| 2. Oversee event set-up. | 2.1. Establish on-site contact with contractors and reconfirm all requirements. 2.2. Assess all aspects of event set-up against prearranged service agreements and check for safety and ease of attendee access. 2.3. Identify deficiencies and discrepancies and take prompt action to resolve. 2.4. Conduct final briefing on event operational details, including communication and control mechanisms. |
| 3. Monitor event operation. | 3.1. Monitor event operation through observation and communication with relevant personnel to ensure effective delivery of services. 3.2. Identify and quickly evaluate operational problems as they arise and take prompt action to resolve. 3.3. Monitor compliance with environmental and social sustainability procedures to ensure minimal impacts. 3.4. Liaise with client throughout event to ensure satisfaction with service delivery and make necessary adjustments. |
| 4. Oversee event break-down. | 4.1. Ensure event break-down is completed according to agreements. 4.2. Check and sign invoices according to contractor agreements. 4.3. Debrief relevant personnel to improve future event service delivery. |
| 5. Evaluate operational success of event. | 5.1. Obtain feedback from customers and seek input from personnel and contractors on event operations. 5.2. Reflect on and evaluate operational problems. 5.3. Provide recommendations for improvements to future event management practices. |

# Foundation Skills

| Foundation skills essential to performance in this unit, but not explicit in the performance criteria are listed here, along with a brief context statement. |  |
| --- | --- |
| SKILLS | DESCRIPTION |
| Reading skills to: | interpret complex event planning documentation. |
| Writing skills to: | write complex and detailed, yet easily accessible, event operational documents. |
| Oral communication skills to: | negotiate solutions and provide clear instructions when problems arise. |
| Numeracy skills to: | interpret event budgets and event service agreement costings to determine correct on-site supply of contracted services work quickly and accurately with budget figures to calculate effect on event profitability when resolving on-site problems. |
| Problem-solving skills to: | negotiate solutions with clients, and internal and external personnel under pressure where time constraints play a key factor. |
| Teamwork skills to: | lead a team of event production personnel and external contractors to effectively deliver events consult with team members and take account of suggested solutions to on-site production problems. |
| Self-management skills to: | take responsibility for the finalisation of event plans and on-site coordination of the delivery of the event. |
| Technology skills to: | use calculators, computers, software programs and printers for processing event documentation use two-way communication equipment for on-site management. |

# Unit Mapping Information

Supersedes and is equivalent to SITEEVT010 Manage on-site event operations.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=68c40a93-e51d-4e0f-bc06-899dff092694