# Assessment Requirements for SITEEVT035 Develop multi-venue event plans

Release: 1

Assessment Requirements for SITEEVT035 Develop multi-venue event plans

# Modification History

Not applicable.

# Performance Evidence

Evidence of the ability to complete tasks outlined in elements and performance criteria of this unit in the context of the job role, and:

determine requirements and select venues for at least one multi-venue event with multiple operational components

conduct planning and risk analysis for the above event, giving consideration to:

risks associated with using multiple venues for events

geographical factors

communication requirements between venues

develop and document details of the following operational procedures and information for the above multi-venue event:

communication protocols

key personnel in each venue

management structures

transport scheduling

contingency procedures

emergency information

event rosters, running sheets and schedules across venues

event uniformity requirements

route maps between venues and sites

information on venues, sites and local area

evaluate stakeholder feedback on the success of the above multi-venue event operations against the following criteria:

communication

contingency management

operational efficiency

profitability

resource efficiency

success in meeting event objectives.

# Knowledge Evidence

Demonstrated knowledge required to complete the tasks outlined in elements and performance criteria of this unit:

types of events that require the use of multiple venues

implications of multi-venue event operations and ways to address them:

communication

management structures

operational complexities

resources:

financial

human

physical

safety

geographical factors:

distance between venues

pick-up and drop-off points

terrain

traffic routes

transport requirements

inter-venue communication options and relevant technologies to suit particular event requirements:

computer networks

telephone systems or teleconferencing

two-way radios

video links or videoconferencing

risk management issues associated with the use of multiple venues for an event:

communication issues

contractor management

consistency of presentation and standards

crowd control

delays

emergency services access

security complications

additional resource and production requirements of a multi-venue event

organisational procedures to gather stakeholder feedback to evaluate events and report on improvements.

# Assessment Conditions

Skills must be demonstrated in:

a live event; or

a simulated industry event set up for the purpose of assessment.

Assessment must ensure access to:

multiple venues and sites where events are operated

event budgets

event plans

current industry documentation and publications relating to venues and sites

formal communications plans

operational information for multi-venue events:

contingency procedures

emergency information

event rosters

event running sheets

event schedules across venues

maps and other geographical information:

route maps between venues and sites

information for venues, sites and local area

an event operations team and event stakeholders with whom the individual consults and venue personnel with whom operational and communication strategies and procedures can be established. These can be:

those in an industry workplace who are assisted by the individual during the assessment process; or

individuals who participate in role plays or simulated activities, set up for the purpose of assessment, in a simulated industry environment operated within a training organisation.

Assessors must satisfy the Standards for Registered Training Organisations’ requirements for assessors and have worked in industry for at least three years where they have applied the skills and knowledge of this unit of competency.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=68c40a93-e51d-4e0f-bc06-899dff092694