# SITXMGT006 Manage projects

Release: 1

SITXMGT006 Manage projects

# Modification History

Not applicable.

# Application

This unit describes the performance outcomes, skills and knowledge required to develop project plans, implement project activities, monitor progress to ensure objectives are achieved, and evaluate all aspects of projects.

The unit applies to all tourism, travel, hospitality and event sectors and the project could relate to event planning and execution, product development, research or initiatives such as the introduction of new workplace systems or technologies.

It applies to senior personnel who operate independently or with limited guidance from others and who are responsible for making a range of operational business and project management decisions.

The skills in this unit must be applied in accordance with Commonwealth and State/Territory legislation, Australian/New Zealand standards and industry codes of practice.

No occupational licensing, certification or specific legislative requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Nil

# Competency Field

Management and Leadership

# Unit Sector

Cross-Sector

# Elements and Performance Criteria

| ELEMENTS | PERFORMANCE CRITERIA |
| --- | --- |
| Elements describe the essential outcomes | Performance criteria describe the performance needed to demonstrate achievement of the element. |
| 1. Define project scope. | 1.1. Identify project objectives, budget, scope of activities and deliverables. 1.2. Clarify relationship of project to others and to overall organisational objectives. 1.3. Identify stakeholders and their requirements for consultation and involvement in project activities. 1.4. Confirm administrative structure for project management, individual responsibility and reporting hierarchy. 1.5. Determine required resources for the project. |
| 2. Develop project plan. | 2.1. Consult with stakeholders to facilitate input and to achieve approval for project plan. 2.2. Determine risk, regulatory and sustainability issues and incorporate into plan. 2.3. Integrate quality, financial, human and physical resource specifications for project activities. 2.4. Develop and integrate project evaluation methods. 2.5. Plan internal and external communications, public relations and marketing approaches. 2.6. Document integrated project management plan. 2.7. Communicate plan and roles and responsibilities to all involved. |
| 3. Administer and monitor project. | 3.1. Implement project activities according to plan and in conjunction with stakeholders and project team members, providing support and assistance as required. 3.2. Implement financial and quality control systems according to project plan. 3.3. Monitor progress to ensure objectives, deliverables, timelines, cost and quality of project are achieved. 3.4. Identify deviations from plan, assess and take action to re-align project activities to meet objectives. 3.5. Determine and act on the need for project variations, including additional project resources. 3.6. Provide progress and final reports according to project requirements. 3.7. Complete project within agreed timelines. |
| 4. Evaluate project. | 4.1. Assess project effectiveness at specified stages using agreed evaluation methods. 4.2. Evaluate completed project for administrative efficiency, quality and achievement of objectives. 4.3. Report outcomes to stakeholders and use information to enhance future project planning and management activities. |

# Foundation Skills

| Foundation skills essential to performance in this unit, but not explicit in the performance criteria are listed here, along with a brief context statement. |  |
| --- | --- |
| SKILLS | DESCRIPTION |
| Reading skills to: | interpret reports, comparing project outcomes against planned deliverables. |
| Writing skills to: | write quantitative and qualitative evaluation criteria. |
| Numeracy skills to: | interpret project budgets for diverse components develop resource specifications within budgetary parameters. |
| Problem-solving skills to: | evaluate and respond to factors within project management activities. |
| Planning and organising skills to: | manage interrelated aspects of a project and project timelines. |
| Technology skills to: | use computers, word processing and software packages for project management. |

# Unit Mapping Information

Supersedes and is equivalent to SITXMGT003 Manage projects.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=68c40a93-e51d-4e0f-bc06-899dff092694

Assessment Requirements for SITXMGT006 Manage projects

# Modification History

Not applicable.

# Performance Evidence

Evidence of the ability to complete tasks outlined in elements and performance criteria of this unit in the context of the job role, and:

develop and implement a plan for a project addressing one or more of the following objectives:

community or industry development

economic or social benefits

education or training

profit

research

administer and monitor the following components of the above project:

dedicated project budget and financial control system

administrative components involving individual responsibility and reporting hierarchy for at least two of the following:

advisory or reference group

consultants, contractors or suppliers

organisational management

project management committee

secretariat

progress against project objectives

quality control system

risk, regulatory and sustainability issues

lead a project team and liaise with a wide range of stakeholders during the planning and implementation phases of the above project, providing at least two of the following forms of support and assistance as appropriate:

additional resources

formal training opportunities

informal coaching and feedback

moderation and joint planning sessions

regular meetings and briefings

representing team interests in wider forums

apply sound administrative processes when planning and implementing the above project within required timeframes.

# Knowledge Evidence

Demonstrated knowledge required to complete the tasks outlined in elements and performance criteria of this unit:

project management processes and the project life cycle:

planning and requirements of project plans:

objectives

deliverables, scheduling and milestones

allocation of roles and responsibilities

documentation and role of technology

monitoring and control systems

evaluation criteria, both quantitative and qualitative, and methods for measuring the success of project objective

project management plan inclusions:

budget

consultation strategies

internal and external communication processes and channels

key milestones

marketing strategies

objectives and outcomes

quality assurance process

reporting requirements

responsibilities of project personnel and stakeholders

risk management and contingency plans

safety initiatives

selection or tendering process

sponsors

stages

sustainability considerations

timeframes

role of project management personnel and stakeholders in the management of projects

reporting hierarchies

administrative structures

risk, regulatory and sustainability issues for project management:

financial management

human resource management

physical resource management

potential stakeholders in a project:

community agencies

customer or client

funding bodies

government departments or statutory authorities

industry associations

internal personnel

management

media

sponsors.

# Assessment Conditions

Skills must be demonstrated in an operational business environment. This can be:

an industry workplace; or

a simulated industry environment set up for the purposes of assessment.

Assessment must ensure access to:

projects to be managed by the individual

information and communications technology currently used to manage projects

physical and financial resources to support the project

project team and stakeholders with whom the individual can interact. These can be:

those in an industry workplace who are assisted by the individual during the assessment process; or

individuals who participate in role plays or simulated activities, set up for the purpose of assessment, in a simulated industry environment operated within a training organisation.

Assessors must satisfy the Standards for Registered Training Organisations’ requirements for assessors.

# Links

Companion Volume implementation guides are found in VETNet - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=68c40a93-e51d-4e0f-bc06-899dff092694