# UEECD0057 Manage electrotechnology projects

Release: 1

UEECD0057 Manage electrotechnology projects

# Modification History

Release 1. This is the first release of this unit of competency in the UEE Electrotechnology Training Package.

# Application

This unit involves the skills and knowledge required to manage an electrotechnology project. It includes determining scope, managing an electrotechnology project and completing reporting/documentation. No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

Not applicable

# Competency Field

Cross Discipline

# Unit Sector

Electrotechnology

# Elements and Performance Criteria

| ELEMENTS |  | PERFORMANCE CRITERIA |  |
| --- | --- | --- | --- |
| Elements describe the essential outcomes. |  | Performance criteria describe the performance needed to demonstrate achievement of the element. |  |
| 1 | Determine scope of the electrotechnology project | 1.1 | Work health and safety (WHS)/occupational health and safety (OHS) procedures for relevant work area are identified and applied |
|  |  | 1.2 | Project deliverables and budget are determined from relevant documentation and discussions with appropriate person/s |
|  |  | 1.3 | Measurable outcomes to evaluate the electrotechnology project are identified from relevant documentation |
|  |  | 1.4 | Resources needed to meet project outcomes are identified from relevant documentation |
|  |  | 1.5 | Processes and procedures are developed for managing contract variations from discussions with relevant person/s and in accordance with contract |
| 2 | Manage the implementation of an electrotechnology project | 2.1 | WHS/OHS policies and procedures are implemented and monitored |
|  |  | 2.2 | Project tasks are delegated to competent project person/s |
|  |  | 2.3 | Project risks are identified, assessed and strategies implemented to ensure outcomes are achieved to relevant industry standards specified in the contract and in accordance with workplace procedures |
|  |  | 2.4 | Procurement is monitored to ensure on-time supply of plant and materials in accordance with project plan and workplace procedures |
|  |  | 2.5 | Verification of project technical design, modification, installation and/or maintenance of system and equipment parameters is completed against specifications and workplace procedures |
|  |  | 2.6 | Project progress is monitored against schedule, quality requirements and budget |
|  |  | 2.7 | Project/worksite conflicts are identified and managed in accordance with workplace procedures |
|  |  | 2.8 | Variations in project are managed in accordance with agreed processes and the contract |
|  |  | 2.9 | Project records are maintained and progress reports completed and provided to appropriate person/s |
| 3 | Complete electrotechnology project | 3.1 | Project outcomes are reviewed against project plan, risk strategies, contract variations, safety performance and budget |
|  |  | 3.2 | Acceptance of project completion is sought from appropriate person/s and handover conducted in accordance with workplace policies and procedures |

# Foundation Skills

Foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Range of Conditions

| Range is restricted to essential operating conditions and any other variables essential to the work environment. Non-essential conditions may be found in the UEE Electrotechnology Training Package Companion Volume Implementation Guide. |  |
| --- | --- |
| Managing electrotechnology projects must include the following: | design modifications installation maintenance of systems and equipment management of: WHS/OHS budget variations personnel resources and critical path timelines progress monitoring completion documentation |

# Unit Mapping Information

This unit replaces and is equivalent to UEENEEE012B Manage electrotechnology projects.

# Links

Companion Volume implementation guides are found in VETNet - - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=b8a8f136-5421-4ce1-92e0-2b50341431b6