# UEEEL0015 Manage large electrical projects

Release: 1

UEEEL0015 Manage large electrical projects

# Modification History

Release 1. This is the first release of this unit of competency in the UEE Electrotechnology Training Package.

# Application

This unit involves the skills and knowledge required to manage large electrical projects. It includes identifying the scope of the project; managing safety, budget variation, personnel, resources and critical path timelines; and completing documentation. No licensing, legislative or certification requirements apply to this unit at the time of publication.

# Pre-requisite Unit

UEECD0007 Apply work health and safety regulations, codes and practices in the workplace

# Competency Field

Electrical

# Unit Sector

Electrotechnology

# Elements and Performance Criteria

| ELEMENTS |  | PERFORMANCE CRITERIA |  |
| --- | --- | --- | --- |
| Elements describe the essential outcomes. |  | Performance criteria describe the performance needed to demonstrate achievement of the element. |  |
| 1 | Identify the scope of the project | 1.1 | Work health and safety (WHS)/occupational health and safety (OHS) processes and workplace procedures for a given work area are identified, obtained and applied |
|  |  | 1.2 | Project deliverables and budget are identified from project planning, relevant documentation and discussions with relevant person/s |
|  |  | 1.3 | Measurable outcomes are identified to evaluate the project on completion from project planning and relevant documentation |
|  |  | 1.4 | Plant, materials and skills required to meet project outcome are identified from project planning and relevant documentation |
|  |  | 1.5 | Processes and workplace procedures are developed for managing contract variations from discussions with relevant person/s and in accordance with contractual agreement |
| 2 | Manage project within scope | 2.1 | WHS/OHS requirements, workplace procedures and programs are implemented and monitored |
|  |  | 2.2 | Achievement of project outcomes is delegated to relevant person/s involved in the project |
|  |  | 2.3 | Risk events are identified and project plan strategies implemented to ensure the outcomes are achieved to a safety and quality standard in accordance with contractual agreement and workplace procedures |
|  |  | 2.4 | Procurement processes are monitored to ensure supply of plant and materials in accordance with workplace procedures |
|  |  | 2.5 | Project progress is monitored in accordance with schedule, quality requirements and budget |
|  |  | 2.6 | Conflict issues on worksite, between stakeholders, clients and regulators are identified and managed in accordance with workplace procedures |
|  |  | 2.7 | Variations are managed in accordance with workplace procedures and contractual agreement |
|  |  | 2.8 | Project records are maintained and progress reports written and forwarded to all relevant person/s |
| 3 | Complete project and relevant documentation | 3.1 | Project outcomes, plan, implemented risk strategies, contract variations, safety record and budget are evaluated in accordance with contractual agreement and workplace procedures |
|  |  | 3.2 | Project completion and acceptance is sought from relevant person/s with relevant documentation in accordance with workplace procedures |

# Foundation Skills

Foundation skills essential to performance are explicit in the performance criteria of this unit of competency.

# Range of Conditions

Range is restricted to essential operating conditions and any other variables essential to the work environment. Non-essential conditions may be found in the UEE Electrotechnology Training Package Companion Volume Implementation Guide.

# Unit Mapping Information

This unit replaces and is equivalent to UEENEEG169A Manage large electrical projects.

# Links

Companion Volume implementation guides are found in VETNet - - https://vetnet.gov.au/Pages/TrainingDocs.aspx?q=b8a8f136-5421-4ce1-92e0-2b50341431b6